## overview mapping
STANDARDS MAPPING OVERVIEW
GAPPS (2011) A Framework for Performance Based Competency Standards for Program Manager | ICB3 | MSP 2011 | The Standard for Program Management, 2nd Edition | P2M
NO Mapping
Provide Leadership for the Program |  |  |  |  | Partial/Some Mapping
1.1 Promote the program vision. |  |  |  |  | Full Mapping
1.1.1 Alignment of the program vision with the vision, mission, principles, and values of the sponsoring organization is maintained. | 1 | 1 | 0.5 | 1
1.1.2 Engagement with the program vision is stimulated through ongoing review, monitoring, communications, and negotiations with pertinent stakeholders. | 0.5 | 1 | 0 | 1
1.1.3 Commitment to the program vision is demonstrated by the program manager. | 1 | 1 | 0.5 | 1
1.2 Build an environment of confidence and trust within the program.
1.2.1 Stakeholders are treated fairly and equitably. | 1 | 1 | 0.5 | 1
1.2.2 Open discussion is encouraged and facilitated. | 1 | 1 | 0 | 1
1.2.3 Differences are managed constructively. | 1 | 0.5 | 0.5 | 1
1.2.4 Issues and concerns are attended to in a timely manner. | 1 | 0.5 | 0 | 1
1.2.5 Interpersonal and leadership styles are chosen and applied based on the circumstances. | 1 | 0.5 | 0.5 | 1
1.2.6 Personal commitments are realistic and honoured. | 1 | 0.5 | 0 | 0
1.3 Embed socially responsible practice into the program.
1.3.1 Expectations for socially responsible practice are made explicit and communicated to constituent projects and other pertinent stakeholders. | 1 | 0 | 0 | 1
1.3.2 Policies and procedures are designed to allow individuals to safely report breaches of socially responsible practice without fear of retaliation. | 0.5 | 0 | 0 | 0.5
1.3.3 Threats to socially responsible practice within the program are identified and addressed. | 1 | 0 | 0 | 0.5
1.4 Develop the potential of program staff.
1.4.1 Individual behavioural expectations for constituent project managers are established. | 1 | 0 | 0 | 1
1.4.2 Individual program roles are defined, documented, communicated, assigned, and agreed to. | 1 | 1 | 0.5 | 0
1.4.3 Desirable behaviours are encouraged, and undesirable behaviours are discouraged. | 1 | 0 | 0 | 1
1.5 Support a learning environment.
1.5.1 Program planning and program plan implementation are viewed as a learning process. | 1 | 1 | 0 | 1
1.5.2 Errors, mistakes, and expressed concerns are treated as learning opportunities. | 0.5 | 1 | 0 | 0.5
1.5.3 Plans for identifying, capturing, disseminating, and exchanging knowledge are developed and maintained. | 0 | 0.5 | 0.5 | 1
1.5.4 Program knowledge is identified, captured, disseminated, and exchanged as planned. | 1 | 0.5 | 0.5 | 1
1.5.5 Reflection on and review of practice is encouraged as a basis for learning. | 1 | 1 | 0.5 | 0.5
Facilitate Stakeholder Engagement
2.1 Communicate effectively with stakeholders.
2.1.1 Program stakeholders and their communication needs are identified and documented. | 1 | 1 | 0.5 | 1
2.1.2 Communication approaches are agreed to by pertinent stakeholders. | 0 | 1 | 0.5 | 1
2.1.3 Information is shared as planned, and variances are identified and addressed. | 1 | 1 | 0.5 | 1
2.1.4 Communication interfaces among constituent projects are monitored. | 0 | 1 | 0.5 | 1
2.2 Cultivate stakeholder commitment.
2.2.1 Interests and expectations of pertinent stakeholders are investigated, documented, and considered when making program decisions. | 1 | 0.5 | 0.5 | 1
2.2.2 Approaches to influence ongoing stakeholder commitment are developed and implemented. | 1 | 0.5 | 0.5 | 1
2.2.3 Actions are taken to accommodate differing stakeholder interests and expectations. | 1 | 0.5 | 1 | 1
2.2.4 Evolving stakeholder interests and expectations are shared across the program. | 0.5 | 0.5 | 1 | 1
Craft the Program
3.1 Envision the desired future state.
3.1.1 Description of the desired future state is defined and agreed to by pertinent stakeholders. | 1 | 1 | 0.5 | 1
3.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the desired future state. | 0 | 1 | 0.5 | 1
3.1.3 The description of the desired future state is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 0.5 | 1 | 0 | 1
3.2 Shape and sustain the program execution approach.
3.2.1 Gaps between the current state and the desired future state are defined and agreed to by pertinent stakeholders. | 0 | 1 | 0.5 | 1
3.2.2 Changes needed to move from the current state to the desired future state are defined and agreed to by pertinent stakeholders. | 1 | 1 | 0.5 | 1
3.2.3 A program execution approach based on changes needed is defined and agreed to by pertinent stakeholders. | 1 | 0.5 | 1 | 1
3.2.4 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program execution approach. | 0.5 | 1 | 0.5 | 1
3.2.5 The program execution approach is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 1 | 1 | 0.5 | 1
3.3 Shape and sustain the program’s business case.
3.3.1 A business case for both the desired future state and the program execution approach is defined, documented, and approved by pertinent stakeholders. | 0.5 | 1 | 0.5 | 1
3.3.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program’s business case. | 0.5 | 1 | 0.5 | 1
3.3.3 The program’s business case is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 0.5 | 1 | 0.5 | 1
3.4 Shape and sustain program governance.
3.4.1 Program organization is defined, maintained, refreshed, and agreed by the sponsoring organization. | 1 | 0.5 | 0 | 1
3.4.2 Program boundaries and governance structures are designed to exploit synergies within the sponsoring organization. | 1 | 0.5 | 0.5 | 1
3.4.3 Policies, processes, and procedures to support the management of the program are identified/devised and communicated to pertinent stakeholders. | 0.5 | 0.5 | 1 | 1
Orchestrate Attainment of Benefits
4.1 Identify benefits and trade-offs.
4.1.1 Expected short- and long-term benefits and trade-offs are defined and communicated to pertinent stakeholders. | 0.5 | 1 | 0.5 | 1
4.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the expected benefits. | 0.5 | 1 | 0.5 | 1
4.1.3 Expected benefits and trade-offs are periodically reviewed and confirmed or updated. | 0.5 | 0.5 | 0.5 | 1
4.2 Shape and sustain benefits delivery approach.
4.2.1 Benefits measurement approach is defined and agreed to by pertinent stakeholders. | 1 | 1 | 0.5 | 0
4.2.2 Benefits delivery approach is devised and agreed to by pertinent stakeholders. | 0.5 | 1 | 0.5 | 0
4.2.3 Ownership of benefits delivery is assigned and accepted. | 0 | 1 | 1 | 0
4.2.4 Benefits measurement approach and benefits delivery approach are reviewed periodically and confirmed or updated. | 0 | 0.5 | 0 | 0
4.3 Evaluate attainment of expected benefits.
4.3.1 Deliverables from constituent projects are assessed in accordance with the benefits measurement approach. | 0 | 1 | 1 | 1
4.3.2 Progress toward delivery of expected benefits is measured and reported to pertinent stakeholders. | 0 | 1 | 1 | 0.5
4.3.3 Variances in delivery of expected benefits are addressed. | 0 | 1 | 1 | 0
Sustain Program Progress
5.1 Secure program funding.
5.1.1 Ongoing funding requirements are determined, documented, and communicated to pertinent stakeholders. | 0.5 | 1 | 0.5 | 0
5.1.2 Funding commitments are secured as needed. | 1 | 0.5 | 0.5 | 0
5.1.3 Funding issues are addressed. | 1 | 0.5 | 0.5 | 0
5.1.4 Funding requirements are satisfied. | 0 | 0 | 0 | 0
5.2 Resource the program.
5.2.1 Program resource requirements are determined, documented, negotiated with, and communicated to pertinent stakeholders. | 1 | 1 | 0.5 | 0.5
5.2.2 Program resources are acquired and coordinated across the program and its constituent projects. | 1 | 1 | 0.5 | 1
5.2.3 Program resource requirements are confirmed or updated in response to program refinements or changes. | 1 | 0.5 | 0.5 | 0.5
5.3 Measure, evaluate, and coordinate program progress.
5.3.1 Monitoring and control systems are established and maintained. | 1 | 1 | 0.5 | 0.5
5.3.2 Monitoring and control systems are used to maintain momentum and support delivery of expected benefits. | 0.5 | 1 | 0.5 | 0.5
5.3.3 Performance of constituent projects and other program elements is reported to pertinent stakeholders. | 1 | 1 | 1 | 0
5.3.4 A sustainable pace is maintained so that the program does not go too slow or too fast. | 0 | 1 | 0 | 0.5
5.4 Ensure relevant legal and regulatory requirements are addressed.
5.4.1 Relevant legal and regulatory requirements are identified, documented, and communicated to pertinent stakeholders. | 1 | 0.5 | 1 | 0
5.4.2 Potential for conflicts caused by legal and regulatory requirements are identified and addressed. | 1 | 0.5 | 0.5 | 0
5.4.3 Compliance policies, processes, and procedures are implemented. | 1 | 0 | 0.5 | 0
5.4.4 Applicable legal and regulatory requirements are monitored for breaches and conflicts. | 1 | 0 | 0.5 | 0
5.5 Anticipate and respond to changes.
5.5.1 Internal and external program contexts are monitored and evaluated for circumstances that may require changes. | 0.5 | 0.5 | 0.5 | 1
5.5.2 Actual and potential changes are identified, documented, and evaluated. | 1 | 1 | 0.5 | 1
5.5.3 Approved changes are implemented. | 1 | 1 | 0.5 | 1
5.5.4 Changes and their implications are communicated to pertinent stakeholders. | 0.5 | 1 | 0.5 | 1
5.6 Manage program risks.
5.6.1 Risk management approach for the program and its constituent projects is documented, communicated, and agreed to by pertinent stakeholders. | 1 | 1 | 0.5 | 0.5
5.6.2 Program risks are identified in consultation with pertinent stakeholders. | 1 | 1 | 0.5 | 0
5.6.3 Program risks are analysed and prioritized, and risk responses are implemented as planned. | 1 | 1 | 1 | 1
5.6.4 Internal and external program contexts are monitored for circumstances that may affect program risks. | 1 | 1 | 0.5 | 1
Manage Organizational Change
6.1 Shape and sustain organizational change implementation approach.
6.1.1 The extent and nature of organizational change required in support of the program is evaluated and periodically re-evaluated. | 0 | 0.5 | 0 | 1
6.1.2 Potential organizational change implementation approaches are identified and evaluated for applicability. | 0 | 1 | 0 | 0.5
6.1.3 The organizational change implementation approach is reviewed periodically and confirmed or modified to ensure support for expected benefits. | 0 | 0.5 | 0 | 0.5
6.1.4 The organizational change implementation approach is coordinated with the program execution approach and accepted by pertinent stakeholders. | 0 | 1 | 0 | 0.5
6.2 Advocate for change with stakeholders.
6.2.1 Approaches for stakeholder engagement in organizational change are devised and deployed. | 0 | 0.5 | 0 | 0.5
6.2.2 Benefits of organizational change are articulated for pertinent stakeholders. | 0 | 0.5 | 0 | 0.5
6.2.3 An organizational change communications plan is documented, maintained, and agreed to by pertinent stakeholders. | 0 | 0.5 | 0 | 0.5
6.2.4 Organizational change communications plan is implemented and variances are addressed. | 0 | 0.5 | 0 | 0.5
6.2.5 Resistance to change is monitored, evaluated, and addressed. | 0 | 0.5 | 0 | 0.5
6.3 Evaluate the effectiveness of the organizational change.
6.3.1 Methods for evaluating the effectiveness of the organizational change initiatives are identified, documented and agreed to by pertinent stakeholders. | 0 | 1 | 0 | 0.5
6.3.2 Selected evaluation methods are applied on an ongoing basis. | 0 | 1 | 0 | 0.5
6.3.3 Feedback is provided to pertinent stakeholders regarding progress of organizational change. | 0 | 1 | 0 | 0.5
6.3.4 Variances in attainment of desired organizational change are addressed. | 0 | 0 | 0 | 0.5
Direct the Management of Contracts
7.1 Shape and sustain contract management approach.
7.1.1 Contract management approach is devised, documented, kept current, and agreed to by pertinent stakeholders. | 0 | 0.5 | 0.5 | 0.5
7.1.2 Policies, processes, and procedures to support the contract management approach are developed, approved, maintained, and communicated to pertinent stakeholders. | 0 | 0.5 | 0.5 | 0
7.1.3 Risk management related to contracts is integrated with overall program risk management. | 0.5 | 0 | 0.5 | 0.5
7.2 Oversee and verify contract performance.
7.2.1 Contracts are approved in accordance with the contract management approach. | 0.5 | 0.5 | 1 | 0
7.2.2 Alignment of contractor performance with contract requirements is verified. | 0.5 | 0.5 | 0.5 | 0.5
7.2.3 Resolution of contract variances is documented and verified. | 0.5 | 0.5 | 0.5 | 0
7.2.4 Mechanisms to support effective communications, coordination, synergies, and integration of contracts with constituent projects in the program are implemented. | 0 | 0 | 0 | 0
7.2.5 Compliance with policies, processes, and procedures is monitored. | 0 | 0 | 0.5 | 0
Engage in Collaborative Alliances
8.1 Cultivate collaborative alliances.
8.1.1 Opportunities for collaborative alliances are identified and evaluated. | 0 | 0 | 0 | 1
8.1.2 Potential collaborators are identified and evaluated. | 0 | 0 | 0 | 0.5
8.1.3 Relationships with potential collaborators are initiated, nuanced, and shaped. | 0 | 0 | 0 | 1
8.2 Devise and elaborate collaborative agreements.
8.2.1 A collaborative agreement approach is initiated, negotiated, documented, and accepted by the parties to each agreement. | 0 | 0 | 0 | 1
8.2.2 Each formal agreement is signed and regularly reviewed to ensure continuation of envisaged value and potential need for changes and additions. | 0 | 0 | 0 | 1
8.2.3 Collaboration plans are developed for each agreement to support implementation. | 0 | 0 | 0 | 1
8.3 Support the evolution of collaborative agreements.
8.3.1 Relationships with collaborators are monitored and nurtured to sustain commitment. | 0 | 0 | 0 | 1
8.3.2 Performance of all parties to an agreement is assessed against expected results and variances are addressed. | 0 | 0 | 0 | 1
8.3.3 Changes to agreements are made as required | 0 | 0 | 0 | 0.5
| 56 | 67 | 39 | 69
Percentage coverage | 53.33% | 63.81% | 37.14% | 65.71%

## ICB V3.0
Mapping: ICB® Version 3.0 to GAPPS Program Manager Standards
The intent of the GAPPS mapping process is to use the GAPPS standards as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. Therefore, this is a mapping of the COVERAGE only of the ICB® v 3.0 at the Element and Process Step level against the GAPPS Project Manager Standards. The ICB® v3.0 includes Technical, Contextual and Behavioural competencies. All of these have been mapped against the GAPPS standards. The process used for mapping of standards against the GAPPS standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS Working Session 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS Working Session 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the GAPPS standards has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. As the GAPPS framework is intended to be used to assess threshold competency — demonstration of the ability to do something at a standard considered acceptable in the workplace - it is expected that the coverage of other standards is most likely to be considerably broader than that of the GAPPS standard. Topics or activities that are included in other standards, but not included in the GAPPS standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the GAPPS standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case the ICB® v3.0) maps against the GAPPS standard. This mapping has been reviewed by IPMA
LEGEND:
NO Mapping
Partial/Some Mapping
Full Mapping
GAPPS (2011) A Framework for Performance Based Competency Standards for Program Manager | ICB® V. 3.0 IPMA (2006) ICB® - IPMA Competence Baseline Version 3.0, Nijkerk, The Netherlands: International Project Management Association.
Provide Leadership for the Program
1.1 Promote the program vision.
1.1.1 Alignment of the program vision with the vision, mission, principles, and values of the sponsoring organization is maintained. | 3.02.4 Align the essential programmes and benefits to the strategic goals of the organisation using the scoring system.
1.1.2 Engagement with the program vision is stimulated through ongoing review, monitoring, communications, and negotiations with pertinent stakeholders. | 2.02.1 Be aware of the requirments of the various interested parties and the circumstances and the interests of the individuals in the project 2.02.2 Be explicit about which interested parties or personal interests can't or won't be served 2.02.3 Examine possibilities to include the interests of the parties define quick wins and incentives 2.02.4 Be sure to understand what parts of the project different members of the team have bought into and be alert to changes within the individuals 2.02.5 Appreciate communicate and/or document achievements promptly and adequatly 2.02.6 Work on a culture that takes pride in the project and the team's achievements. Provide regular feedback to the team and it's individuals and keep everyone onboard 2.02.7 Be aware of possible changes in interested parties or their interests and act accordingly
1.1.3 Commitment to the program vision is demonstrated by the program manager. | 2.01 Leadership Behavioural Patterns - Has a vision, expresses it very clearly, supports it well and brings it to life
1.2 Build an environment of confidence and trust within the program.
1.2.1 Stakeholders are treated fairly and equitably. | 1.02 Interested Parties 2.14.1 Ensure that your own values as they relate to the project are well understood by all interested parties. 2.14.2 Consider the values, opinions, ethics and interests of different parties who have influence in the political and social sphere in the organisation and outside world. 2.14.3 Take account of prevailing values in society (as influenced by political opinion, pressure group, interested parties and so on) as they may affect the project. 2.14.4 Introduce the values of the people you are communicating and cooperating with into the debate. 2.14.5 Understand or adopt an alternative point of view, where appropriate. 2.14.6 Respect and appreciate other opinions.
1.2.2 Open discussion is encouraged and facilitated. | 2.06.4 Use open questions. 2.06.5 Create opportunities to stimulate openness in the team. 2.13.3 Is honest and creates openness with all individuals and group representatives involved with the project based on mutual respect.
1.2.3 Differences are managed constructively. | 2.12.2.1 Be sure that the project manager isn't personally involved and part of the conflict or crisis. In that case it is wise to let the project owner/senior management know so that they can assign someone else to resolve the conflict or crisis. 2.12.2.2 Consider the conflict or crisis from all parties' viewpoints. 2.12.2.3 Consider what approach to use to resolve the situations or whether to seek mediation using a third party. 2.12.2.4 Consider options to resolve the situation, balancing the interests of all parties. 2.12.2.5 Discuss, decide and communicate the agreed solution.
1.2.4 Issues and concerns are attended to in a timely manner. | 2.14.7 React quickly to changing situations and give adequate consideration to their impact on changing the context of the project.
1.2.5 Interpersonal and leadership styles are chosen and applied based on the circumstances. | 2.01.1 Determine what leadership style is appropriate for the particular situation (with the team, senior management; interested parties). 2.01.2 Ensure it is compatible with your own style and abilities. 2.01.3 Use the chosen leadership style.
1.2.6 Personal commitments are realistic and honoured. | 2.02.4 Be sure to understand what parts of the project different members of the team have bought into and be alert to changes in motivation levels. 2.02.5 Appreciate, communicate and/or document achievements promptly and adequatly. 2.02.6 Work on a culture which takes pride in the project and the teams achievements, provide regular feedback to the team and its individuals and keep everyone involved. 2.13.1 Is well organised, uses appropriate planning and scheduling techniques and maintains adequate communicated with interested parties. 2.13.7 Executes and manages the work performed systematically.
1.3 Embed socially responsible practice into the program.
1.3.1 Expectations for socially responsible practice are made explicit and communicated to constituent projects and other pertinent stakeholders. | 2.15.4 Be very explicit in explaining which ethical issues concern you. 2.15.5 If a colleague insists on continuing on what you consider to be an unethical course of action be understanding and try o resolve the issue amicably. Where that fails, insist that the issue is escalated in the organisation for resolution and/or that mediation takes place.
1.3.2 Policies and procedures are designed to allow individuals to safely report breaches of socially responsible practice without fear of retaliation. | 2.06 Openess 2.15.5 If a colleague insists on continuing on what you consider to be an unethical course of action be understanding and try to resolve the issue amicably. Where that fails, insist that the issue is escalated in the organisation for resolution and/or that mediation takes place.
1.3.3 Threats to socially responsible practice within the program are identified and addressed. | 2.15.2 Detect possible unethical situations arising, or proposals being made, that affect the project and individuals working on it; be sure to maintain transparency in bringing such issues into the open and resolving differences. 2.15.5 If a colleague insists on continuing on what you consider to be an unethical course of action be understanding and try to resolve the issue amicably. Where that fails, insist that the issue is escalated in the organisation for resolution and/or that mediation takes place.
1.4 Develop the potential of program staff.
1.4.1 Individual behavioural expectations for constituent project managers are established. | 1.07.1 Form - develop a common sense of purpose, belonging and commitment. 1.07.3 Norm - openness in how team members can work together. 2.01.1 Determine what leadership style is appropriate for the particular situation (with the team, senior management; interested parties). 2.01.2 Ensure it is compatible with your own style and abilities. 2.01.3 Use the chosen leadership style. 3.08.3 Explain to each project team member what is expected from him and assess the individual's personal circumstances, motivation, interests and goals.
1.4.2 Individual program roles are defined, documented, communicated, assigned, and agreed to. | 1.06.3. Define the roles, responsibilities, interfaces, levels of authority and procedures in the project. 3.08.3 Explain to each project team member what is expected from him and assess the individual's personal circumstances, motivation, interests and goals.
1.4.3 Desirable behaviours are encouraged, and undesirable behaviours are discouraged. | Desirable and Undesirable tables throughout Section 2
1.5 Support a learning environment.
1.5.1 Program planning and program plan implementation are viewed as a learning process. | 1.01.7 Evaluate PM successes and failures, transfer and apply lessons learnt to future projects. 3.11.7 Document lessons learnt. Note: the following sections also map to this - 1.02.11, 1.03.8, 1.04.7, 1.05.7, 1.06.9, 1.07.6, 1.08.7, 1.09.7, 1.10.7, 1.11.7, 1.12.9, 1.13.11.1, 1.13.10.2, 1.14.8, 1.15.9, 1.16.8, 1.17.6.1, 1.17.8.2, 1.18.9, 1.19.10, 1.20.12, 2.01.8, 2.02.8, 2.03.9, 2.04.9, 2.05.6, 2.06.7, 2.07.8, 2.08.10, 2.09.10, 2.10.8, 2.11.8, 2.12.2.6. 2.13.8, 2.14.8, 2.15.8, 3.01.5, 3.02.8, 3.04.8, 3.06.5, 3.07.12.1, 3.07.9.2, 3.08.8, 3.09.7, 3.10.6, 3.11.8
1.5.2 Errors, mistakes, and expressed concerns are treated as learning opportunities. | 2.03.9 Learn from stressful situations and loss of self control; use the knowledge to minimize the impact of such situations when they happen in the future 2.06.7 Learn from each situation and continue to improve your methods of openess
1.5.3 Plans for identifying, capturing, disseminating, and exchanging knowledge are developed and maintained.
1.5.4 Program knowledge is identified, captured, disseminated, and exchanged as planned. | 1.01.7 Evaluate PM successes and failures, transfer and apply lessons learnt to future projects. 2.08.10 Documents lessons learnt and implement changes in future projects or phases of the project. 1.20.12 Update the lessons learnt database and apply to future projects 1.16.8 Document the lessons learnt and apply to future projects 3.05.7 Monitor progress, implement learning cycle 3.06.5 Provide feedback on lessons learned and apply in the permanent organisation and/or portfolio/program/project organisation as appropriate
1.5.5 Reflection on and review of practice is encouraged as a basis for learning. | 1.01.7 Evaluate PM successes and failures, transfer and apply lessons learnt to future projects. 2.01.4 Review performance and seek feedback (from the team, senior management, interested parties; as appropriate) and modify leadership style if necessary. 2.01.7 Review and seek continuous improvement in your own and team members' competence in leadership.
Facilitate Stakeholder Engagement
2.1 Communicate effectively with stakeholders.
2.1.1 Program stakeholders and their communication needs are identified and documented. | 1.18.1 Set out the communication plan at the start of the project or programme, or as one of the portfolio processes 1.18.2 Identify the target population for communication and their location. 1.18.3 Determine what needs to be communicated and the context. 1.18.4 Chose the place, time, duration and means of communication 1.18.5 Plan the communication process and prepare material.
2.1.2 Communication approaches are agreed to by pertinent stakeholders. |  | .
2.1.3 Information is shared as planned, and variances are identified and addressed. | 1.18.6 Check the infrastructure and send/transmit communication. 1.18.7 Seek feedback on the effectiveness of the communication. 1.18.8 Evaluate and take appropriate action.
2.1.4 Communication interfaces among constituent projects are monitored.
2.2 Cultivate stakeholder commitment.
2.2.1 Interests and expectations of pertinent stakeholders are investigated, documented, and considered when making program decisions. | 1.02.1. Identify and prioritise the interested parties’ interests. 1.02.2. Analyse their interests and requirements. 1.02.3. Communicate to interested parties, which of their requirements will be fulfilled or not 1.02.4. Develop a strategy to cope with the interested parties; 1.02.5. Include interested parties’ interests and expectations in the requirements, objectives, scope, deliverables, time schedule and costs of the project management plan.
2.2.2 Approaches to influence ongoing stakeholder commitment are developed and implemented. | 2.02.1 Be aware of the requirments of the various interested parties and the circumstances and the interests of the individuals in the project 2.02.2 Be explicit about which interested parties or personal interests can't or won't be served 2.02.3 Examine possibilities to include the interests of the parties define quick wins and incentives 2.02.4 Be sure to understand what parts of the project different members of the team have bought into and be alert to changes within the individuals 2.02.5 Appreciate communicate and/or document achievements promptly and adequatly 2.02.6 Work on a culture that takes pride in the project and the team's achievements. Provide regular feedback to the team and it's individuals and keep everyone onboard 2.02.7 Be aware of possible changes in interested parties or their interests and act accordingly
2.2.3 Actions are taken to accommodate differing stakeholder interests and expectations. | 1.02.4. Develop a strategy to cope with the interested parties. 1.02.7. Identify the decision escalation process between the project team and the interested parties.
2.2.4 Evolving stakeholder interests and expectations are shared across the program. | 1.02.3 Communicate to interested parties which of their requirements will be fulfilled or not fulfilled by the project 2.02.3 Examine possibilities to include the interests of all parties, define quick wins and incentives
Craft the Program
3.1 Envision the desired future state.
3.1.1 Description of the desired future state is defined and agreed to by pertinent stakeholders. | 1.19.3 Create a shared vision or mission for the programme or project in the plans. 1.19.5 Gain acceptance for the programme or project management plan.
3.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the desired future state.
3.1.3 The description of the desired future state is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 1.03.5 Validate requirements at key points in the project lifecylce
3.2 Shape and sustain the program execution approach.
3.2.1 Gaps between the current state and the desired future state are defined and agreed to by pertinent stakeholders. | 1.16.1 Establish an effective reporting system 1.16.2 Monitor project status and performance on specific dates 1.16.3 Analyse objectives, plans and identify any deviations run trend forecasts 1.16.4 Plan alternatives and run simulations what-if and trade-off analysis 1.16.6 Eventually adjust project objectives
3.2.2 Changes needed to move from the current state to the desired future state are defined and agreed to by pertinent stakeholders. | 1.16.5 Develop and apply corrective actions 1.02.8 Ensure the interested parties are satisfied in each project phase 1.15.4 Seek authorisations for the changes as necessary 1.15.5 Get changes accepted or rejected 1.15.6 Plan execute control and close approved changes
3.2.3 A program execution approach based on changes needed is defined and agreed to by pertinent stakeholders. | 1.19.4 Develop a detailed programme or project management plan. 1.19.5 Gain acceptance for the programme or project management plan.
3.2.4 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program execution approach. | 3.03.5 Delete programmes/projects from the portfolio when they are no longer relevant / the business strategy has changed and ensure there is a feedback mechanism for lessons learnt.
3.2.5 The program execution approach is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 1.19.9 Agree programme/project charter and programme/project management plan, review at every phase of the programme/project and its projects/sub-projects and modify as necessary.
3.3 Shape and sustain the program’s business case.
3.3.1 A business case for both the desired future state and the program execution approach is defined, documented, and approved by pertinent stakeholders. | 3.02.1 List and prioritise business improvement initiatives. 3.02.2 Confirm that there is a business case to apply programme management. 3.06.4 Implement business change strategy, management reporting and business case requirements
3.3.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program’s business case. | 3.03.5 Delete programmes/projects from the portfolio when they are no longer relevant / the business strategy has changed and ensure there is a feedback mechanism for lessons learnt.
3.3.3 The program’s business case is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 3.03.5 Delete programmes/projects from the portfolio when they are no longer relevant / the business strategy has changed and ensure there is a feedback mechanism for lessons learnt.
3.4 Shape and sustain program governance.
3.4.1 Program organization is defined, maintained, refreshed, and agreed by the sponsoring organization. | 3.06.1 Set up the line organisation and the organisation for projects and program and/or portfolio 3.05.3 Identify and develop interfaces between the permanent and project based parts of the organisation
3.4.2 Program boundaries and governance structures are designed to exploit synergies within the sponsoring organization. | 3.05.1 Understand the organisational structure, objectives and ways of working 3.05.2 Consider interested partiies structure, objectives and ways of working 3.05.3 Identify and develop interfaces between the permanent and project based parts of the organisation 3.05.4 Identify commonalities and differences 3.05.5 Consider options and sequences of each
3.4.3 Policies, processes, and procedures to support the management of the program are identified/devised and communicated to pertinent stakeholders. | 1.19.4 Develop a detailed programme or project management plan. 3.05.6 Discuss, decide, communicate implement 3.06.4 Implement business change strategy, management reporting and busines case requirements
Orchestrate Attainment of Benefits
4.1 Identify benefits and trade-offs.
4.1.1 Expected short- and long-term benefits and trade-offs are defined and communicated to pertinent stakeholders. | 3.02.4 Align the essential programmes and benefits to the strategic goals of the organisation using the scoring system. 3.06.4 Implement business change strategy, management reporting and busines case requirements
4.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the expected benefits. | 3.03.5 Delete programmes/projects from the portfolio when they are no longer relevant / the business strategy has changed and ensure there is a feedback mechanism for lessons learnt.
4.1.3 Expected benefits and trade-offs are periodically reviewed and confirmed or updated. | 3.03.4 Continuously monitor and control the programmes/projects of the portfolio. Initiate corrective actions.
4.2 Shape and sustain benefits delivery approach.
4.2.1 Benefits measurement approach is defined and agreed to by pertinent stakeholders. | 3.02.3 Introduce a scoring system to quantify essential (core) programmes and their benefits. 3.02.4 Align the essential programmes and benefits to the strategic goals of the organisation using the scoring system.
4.2.2 Benefits delivery approach is devised and agreed to by pertinent stakeholders. | 3.02.5 Review output with appropriate management level; make and communicate decisions. 3.06.4 Implement business change strategy, management reporting and busines case requirements
4.2.3 Ownership of benefits delivery is assigned and accepted.
4.2.4 Benefits measurement approach and benefits delivery approach are reviewed periodically and confirmed or updated.
4.3 Evaluate attainment of expected benefits.
4.3.1 Deliverables from constituent projects are assessed in accordance with the benefits measurement approach.
4.3.2 Progress toward delivery of expected benefits is measured and reported to pertinent stakeholders.
4.3.3 Variances in delivery of expected benefits are addressed.
Sustain Program Progress
5.1 Secure program funding.
5.1.1 Ongoing funding requirements are determined, documented, and communicated to pertinent stakeholders. | 1.13.1 Analyse financing options/models for project, programme or portfolio 1.13.2. Negotiate with possible sources of funds and determine conditions attached.
5.1.2 Funding commitments are secured as needed. | 1.13.2. Negotiate with possible sources of funds and determine conditions attached. 1.13.3. Select source of project funding. 1.13.4. Allocate budget to cost items, analyse advance payments.
5.1.3 Funding issues are addressed. | 1.13.1 Analyse financing options/models for project, programme or portfolio 1.13.8. Take into account modification of financial resource usage and budgets available during the project life-cycle. 1.13.9. Validate and manage budgets, covering incurred costs.
5.1.4 Funding requirements are satisfied.
5.2 Resource the program.
5.2.1 Program resource requirements are determined, documented, negotiated with, and communicated to pertinent stakeholders. | 1.12.1 Identify what resources are required including the specific project mangement effort, the competencies required of the personnel in the project team should also be made explict 1.12.2 Schedule the resources 1.12.3 Obtain agreement with the line mangement for resource assignment to the project 1.12.4 Place the estimates and the resource assignments plan under change control 2.09.2 Plan the necessary activities, obtain resources and assign them to deliver a given task, adding a contingency factor where appropriate.
5.2.2 Program resources are acquired and coordinated across the program and its constituent projects. | 3.03.2 Allocate resources to the portfolio. Balance supply with demand. 1.12.5 Manage assignments with the specific emphasis on the productivity of newly appointed personnel 1.12.6 Control the resources with respect to changes 1.12.7 Where resources have been over or underetimated escalate to program or board or portfolio level for resource reallocation
5.2.3 Program resource requirements are confirmed or updated in response to program refinements or changes. | 1.13.8. Take into account modification of financial resource usage and budgets available during the project life-cycle. 1.13.9. Validate and manage budgets, covering incurred costs. 3.03.4 Continuously monitor and control the programmes/projects of the portfolio. Initiate corrective actions.
5.3 Measure, evaluate, and coordinate program progress.
5.3.1 Monitoring and control systems are established and maintained. | 1.13.5. Calculate financial resource usage and cash-in and cash-out flows of the project, programme or portfolio. 1.13.6. Establish and control process and authorisation for payments. 1.13.7. Recognise or establish and control book-keeping and financial auditing systems. 3.03.4 Continuously monitor and control the programmes/projects of the portfolio. Initiate corrective actions.
5.3.2 Monitoring and control systems are used to maintain momentum and support delivery of expected benefits. | 3.03.4 Continuously monitor and control the programmes/projects of the portfolio. Initiate corrective actions.
5.3.3 Performance of constituent projects and other program elements is reported to pertinent stakeholders. | 1.16.2 Monitor project status and performance on specific dates. 1.16.7 Report project status and performance to interested parties.
5.3.4 A sustainable pace is maintained so that the program does not go too slow or too fast.
5.4 Ensure relevant legal and regulatory requirements are addressed.
5.4.1 Relevant legal and regulatory requirements are identified, documented, and communicated to pertinent stakeholders. | 2.15.1 Ensure conformity to any legal or regulatory framework that applies to the project. 3.11.1 Set legal standards and guidelines appropriate to the organisation or portfolio. 3.11.2 Initiate processes for implementing appropriate standards and guidelines in the organisation or portfolio and evaluate projects and programmes against these standards and guidelines. 3.11.3 Investigate and describe for the organisation or portfolio the relevant legal aspects that could apply to a project or programme. 3.11.4 Manage the project's or programme's contracts, claims and changes appropriately.
5.4.2 Potential for conflicts caused by legal and regulatory requirements are identified and addressed. | 3.11.4 Manage the project's or programme's contracts, claims and changes appropriately. 3.11.5 Respond effectively to organised labour challenges. 3.11.6 Respond appropriately to claims of harassment, discrimination, safety issues or non-performance.
5.4.3 Compliance policies, processes, and procedures are implemented. | 3.11.2 Initiate processes for implementing appropriate standards and guidelines in the organisation or portfolio and evaluate projects and programmes against these standards and guidelines.
5.4.4 Applicable legal and regulatory requirements are monitored for breaches and conflicts. | 3.11.2 Initiate processes for implementing appropriate standards and guidelines in the organisation or portfolio and evaluate projects and programmes against these standards and guidelines. 3.11.4 Manage the projects or program contracts, claims and changes appropriately 3.11.5 Respond effectively to organised labour changes 3.11.6 Respond appropriately to claims of harassment, discriminations, safety issues or non-performance
5.5 Anticipate and respond to changes.
5.5.1 Internal and external program contexts are monitored and evaluated for circumstances that may require changes. | 3.03.5 Delete programmes/projects from the portfolio when they are no longer relevant / the business strategy has changed and ensure there is a feedback mechanism for lessons learnt.
5.5.2 Actual and potential changes are identified, documented, and evaluated. | 1.15.2 Identify all proposed changes. 1.15.3 Analyse their consequences to the project.
5.5.3 Approved changes are implemented. | 1.15.4 Seek authorisation for the changes, where necessary. 1.15.5 Get changes accepted or rejected. 1.15.6 Plan. Execute, control and close approved changes.
5.5.4 Changes and their implications are communicated to pertinent stakeholders. | 1.15.7 Report status of changes after completion.
5.6 Manage program risks.
5.6.1 Risk management approach for the program and its constituent projects is documented, communicated, and agreed to by pertinent stakeholders. | 1.04.2 Develop a risk and opportunity response plan and have it approved and communicated.
5.6.2 Program risks are identified in consultation with pertinent stakeholders. | 1.02.6. Place under risk management the threats and opportunities represented by the interested parties. 1.04.1 Identify and assess risks and opportunities
5.6.3 Program risks are analysed and prioritized, and risk responses are implemented as planned. | 1.02.6. Place under risk management the threats and opportunities represented by the interested parties. 1.04.3 Update the different project plans affected by the approved risks and opportunities response plan. 1.04.6 Control the risk and opportunity response plan.
5.6.4 Internal and external program contexts are monitored for circumstances that may affect program risks. | 1.04.5 Continuously identify new risks, reassess risks, plan responses and modify the project plan.
Manage Organizational Change
6.1 Shape and sustain organizational change implementation approach.
6.1.1 The extent and nature of organizational change required in support of the program is evaluated and periodically re-evaluated.
6.1.2 Potential organizational change implementation approaches are identified and evaluated for applicability.
6.1.3 The organizational change implementation approach is reviewed periodically and confirmed or modified to ensure support for expected benefits.
6.1.4 The organizational change implementation approach is coordinated with the program execution approach and accepted by pertinent stakeholders.
6.2 Advocate for change with stakeholders.
6.2.1 Approaches for stakeholder engagement in organizational change are devised and deployed.
6.2.2 Benefits of organizational change are articulated for pertinent stakeholders.
6.2.3 An organizational change communications plan is documented, maintained, and agreed to by pertinent stakeholders.
6.2.4 Organizational change communications plan is implemented and variances are addressed.
6.2.5 Resistance to change is monitored, evaluated, and addressed.
6.3 Evaluate the effectiveness of the organizational change.
6.3.1 Methods for evaluating the effectiveness of the organizational change initiatives are identified, documented and agreed to by pertinent stakeholders.
6.3.2 Selected evaluation methods are applied on an ongoing basis.
6.3.3 Feedback is provided to pertinent stakeholders regarding progress of organizational change.
6.3.4 Variances in attainment of desired organizational change are addressed.
Direct the Management of Contracts
7.1 Shape and sustain contract management approach.
7.1.1 Contract management approach is devised, documented, kept current, and agreed to by pertinent stakeholders.
7.1.2 Policies, processes, and procedures to support the contract management approach are developed, approved, maintained, and communicated to pertinent stakeholders.
7.1.3 Risk management related to contracts is integrated with overall program risk management. | 1.02.6. Place under risk management the threats and opportunities represented by the interested parties. 1.04.3 Update the different project plans affected by the approved risks and opportunities response plan. 1.04.6 Control the risk and opportunity response plan.
7.2 Oversee and verify contract performance.
7.2.1 Contracts are approved in accordance with the contract management approach. | 1.14.4 Establish contract administration.
7.2.2 Alignment of contractor performance with contract requirements is verified. | 3.11.4 Manage the project's or programme's contracts, claims and changes appropriately.
7.2.3 Resolution of contract variances is documented and verified. | 3.11.4 Manage the project's or programme's contracts, claims and changes appropriately.
7.2.4 Mechanisms to support effective communications, coordination, synergies, and integration of contracts with constituent projects in the program are implemented.
7.2.5 Compliance with policies, processes, and procedures is monitored.
Engage in Collaborative Alliances
8.1 Cultivate collaborative alliances.
8.1.1 Opportunities for collaborative alliances are identified and evaluated.
8.1.2 Potential collaborators are identified and evaluated.
8.1.3 Relationships with potential collaborators are initiated, nuanced, and shaped.
8.2 Devise and elaborate collaborative agreements.
8.2.1 A collaborative agreement approach is initiated, negotiated, documented, and accepted by the parties to each agreement.
8.2.2 Each formal agreement is signed and regularly reviewed to ensure continuation of envisaged value and potential need for changes and additions.
8.2.3 Collaboration plans are developed for each agreement to support implementation.
8.3 Support the evolution of collaborative agreements.
8.3.1 Relationships with collaborators are monitored and nurtured to sustain commitment.
8.3.2 Performance of all parties to an agreement is assessed against expected results and variances are addressed.
8.3.3 Changes to agreements are made as required

## MSP 2011
Mapping: Managing Succesful Programs 2011 to GAPPS Program Manager Standards
The intent of the GAPPS mapping process is to use the GAPPS standards as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. Therefore, this is a mapping of the COVERAGE only of the MSP 2011 Heading and Sub-heading Levl. All of these have been mapped against the GAPPS standards. The process used for mapping of standards against the GAPPS standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS Working Session 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS Working Session 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the GAPPS standards has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. As the GAPPS framework is intended to be used to assess threshold competency — demonstration of the ability to do something at a standard considered acceptable in the workplace - it is expected that the coverage of other standards is most likely to be considerably broader than that of the GAPPS standard. Topics or activities that are included in other standards, but not included in the GAPPS standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the GAPPS standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case MSP 2011) maps against the GAPPS standard.
LEGEND:
NO Mapping
Partial/Some Mapping
Full Mapping
GAPPS (2011) A Framework for Performance Based Competency Standards for Program Manager | Managing Successful Programs (MSP) Cabinet Office (2011)
Provide Leadership for the Program
1.1 Promote the program vision.
1.1.1 Alignment of the program vision with the vision, mission, principles, and values of the sponsoring organization is maintained. | 2.1.1 Remaining Aligned with Corporate Strategy 10.2.1 Programme Mandate
1.1.2 Engagement with the program vision is stimulated through ongoing review, monitoring, communications, and negotiations with pertinent stakeholders. | 2.2.3 Envisioning and Communicating a Better Future 5.3 Developing and Maintaing the Vision Statement
1.1.3 Commitment to the program vision is demonstrated by the program manager. | 2.2.3 Envisioning and Communicating a Better Future 4.3 Programme Leadership 5.3 Developing and Maintaing the Vision Statement 5.5 Key roles
1.2 Build an environment of confidence and trust within the program.
1.2.1 Stakeholders are treated fairly and equitably. | 2.2.2 Leading Change 6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership
1.2.2 Open discussion is encouraged and facilitated. | 2.2.2 Leading Change 4.8.2 Key Attributes of the Programme Manager
1.2.3 Differences are managed constructively. | 4.8.2 Key Attributes of the Programme Manager
1.2.4 Issues and concerns are attended to in a timely manner. | 4.8.2 Key Attributes of the Programme Manager
1.2.5 Interpersonal and leadership styles are chosen and applied based on the circumstances. | 4.3 Programme Leadership 4.5.3 Sponsoring Group Formality 4.14 Implementing and Managing the Organization | Suggestion to change to green not accepted based on the following: 4.3 could not find any reference to the selection of program manager based on an indentified leadership style 4.5.3 refers to establishing a style however it doesn't explicitly discuss selecting and modifying your style to suit the context 4.14 No reference to styles of leadership
1.2.6 Personal commitments are realistic and honoured. | 4.8.2 Key Attributes of the Programme Manager
1.3 Embed socially responsible practice into the program.
1.3.1 Expectations for socially responsible practice are made explicit and communicated to constituent projects and other pertinent stakeholders.
1.3.2 Policies and procedures are designed to allow individuals to safely report breaches of socially responsible practice without fear of retaliation.
1.3.3 Threats to socially responsible practice within the program are identified and addressed.
1.4 Develop the potential of program staff.
1.4.1 Individual behavioural expectations for constituent project managers are established. |  | Suggestion to change not accepted based on the following: 9.3.6 This section does not refer to the requirement for the program manager to set behavioural expectations for the project, it talks about management processes and having clearly assigned roles but this is not enough to map to the intention of the GAPPS
1.4.2 Individual program roles are defined, documented, communicated, assigned, and agreed to. | 4.4 Programme Structure 4.16 Key Roles
1.4.3 Desirable behaviours are encouraged, and undesirable behaviours are discouraged.
1.5 Support a learning environment.
1.5.1 Program planning and program plan implementation are viewed as a learning process. | 2.2.7 Learning from Experience
1.5.2 Errors, mistakes, and expressed concerns are treated as learning opportunities. | 12.2.2.8 People Management
1.5.3 Plans for identifying, capturing, disseminating, and exchanging knowledge are developed and maintained. | 2.2.7 Learning from Experience
1.5.4 Program knowledge is identified, captured, disseminated, and exchanged as planned. | 2.2.7 Learning from Experience 16.13 Prepare for Next Tranche
1.5.5 Reflection on and review of practice is encouraged as a basis for learning. | 12.2.1 Quality and the Programme Management Principles 12.2.2.8 People Management
Facilitate Stakeholder Engagement
2.1 Communicate effectively with stakeholders.
2.1.1 Program stakeholders and their communication needs are identified and documented. | 6.6 Steps Involved in Stakeholder Engagement 6.8 Key Roles 9.5 Key Roles
2.1.2 Communication approaches are agreed to by pertinent stakeholders. | 6.5 Communications with the projects & other programs 6.6 Steps Involved in Stakeholder Engagement
2.1.3 Information is shared as planned, and variances are identified and addressed. | 6.8 Key Roles 9.5 Key Roles
2.1.4 Communication interfaces among constituent projects are monitored. | 6.5 Communications with the projects & other programs 6.6 Steps Involved in Stakeholder Engagement
2.2 Cultivate stakeholder commitment.
2.2.1 Interests and expectations of pertinent stakeholders are investigated, documented, and considered when making program decisions. | 6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership
2.2.2 Approaches to influence ongoing stakeholder commitment are developed and implemented. | 6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership
2.2.3 Actions are taken to accommodate differing stakeholder interests and expectations. | 6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership
2.2.4 Evolving stakeholder interests and expectations are shared across the program. | 6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership
Craft the Program
3.1 Envision the desired future state.
3.1.1 Description of the desired future state is defined and agreed to by pertinent stakeholders. | 5.2 Characteristics of a good vision statement 5.3 Developing and Maintaing the Vision Statement
3.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the desired future state. | 5.3 Developing and Maintaing the Vision Statement
3.1.3 The description of the desired future state is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 16. Manage the Tranches 16.7 Maintain alignment between programme bliueprint and business strategic objectives 16.14 End of Tranche review and close | Suggestion to change to green accepted
3.2 Shape and sustain the program execution approach.
3.2.1 Gaps between the current state and the desired future state are defined and agreed to by pertinent stakeholders. | 8.2 Blueprint Design 8.2.1 Future State 8.2.2 Current State & Gap Analysis 8.3 Designing the Blueprint Delivery 8.5 Key Roles
3.2.2 Changes needed to move from the current state to the desired future state are defined and agreed to by pertinent stakeholders. | 8.2 Blueprint Design 8.2.1 Future State 8.2.2 Current State & Gap Analysis 8.3 Designing the Blueprint Delivery 8.5 Key Roles
3.2.3 A program execution approach based on changes needed is defined and agreed to by pertinent stakeholders. | 3.3.3 Programme Management Strategies and Plan 9.2 Programme Plan
3.2.4 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program execution approach. | 18.2.2 Monitor Benefits Realisation
3.2.5 The program execution approach is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 18.2.2 Monitor Benefits Realisation
3.3 Shape and sustain the program’s business case.
3.3.1 A business case for both the desired future state and the program execution approach is defined, documented, and approved by pertinent stakeholders. | 10.2.2 Programme Brief 10.3 Contents of the Business Case 15.15 Develop and Confirm Programme Business Case
3.3.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program’s business case. | 10.3 Contents of the Business Case
3.3.3 The program’s business case is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 10.3 Contents of the Business Case
3.4 Shape and sustain program governance.
3.4.1 Program organization is defined, maintained, refreshed, and agreed by the sponsoring organization. | 3.5 Key Roles 4. Programme Organisation 4.1 Introduction 4.2 Programme Organisation Characteristics 4.3 Programme Leadership 4.4 Programme Structure 4.14 Implementing and Managing the Programme Organisation | Suggestions not actioned as they appear to be interpretations of the MSP sections and a mapping must take a direct one-to-one alignment. In details GAPPS 15.8 could not find anything in 15.8 that related to formal endorsement as described in the feedback notes 16.3 could not find a correlation between the feedback interpretation of this section and the actual words in the standard 16.15 provides a suggested set of responsibilities which could be used for defining the program organisation for managing tranches but it doesn't expicitly align these to developing a program organisation maintaining it or getting agreement
3.4.2 Program boundaries and governance structures are designed to exploit synergies within the sponsoring organization. | 3.5 Key Roles 3.2 Integrating Programme Management into the Organisation Control Framework
3.4.3 Policies, processes, and procedures to support the management of the program are identified/devised and communicated to pertinent stakeholders. | 3. Governance Themes Overview (figure 3.1) 3.1 Explanation of the Themes in this Guide
Orchestrate Attainment of Benefits
4.1 Identify benefits and trade-offs.
4.1.1 Expected short- and long-term benefits and trade-offs are defined and communicated to pertinent stakeholders. | 7.4.1 Identify Benefits 18.4.1 Measure Benefits 8.2 Blueprint Design 5.4.3 The Vision during Managing the Tranches Fig 6.2 Engage stakeholders | Slightly ambiguous comment regarding existing mapping the word "additionaly" is followed by only elements that were already included in the mapping. The suggested additional element of 16.5 has not been accepted as it is tangential to the GAPPS performance criteria not critical and it is already a green mapping
4.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the expected benefits. | 2.2.5 Adding Value 18.2.2 Monitor Benefits Realisation
4.1.3 Expected benefits and trade-offs are periodically reviewed and confirmed or updated. | 10.6.4 Delivering the Capability
4.2 Shape and sustain benefits delivery approach.
4.2.1 Benefits measurement approach is defined and agreed to by pertinent stakeholders. | 7.4.1 Identify Benefits 7.4.1.2 Benefits Management Strategy 18.4.1 Measure Benefits
4.2.2 Benefits delivery approach is devised and agreed to by pertinent stakeholders. | 7.4.2.3 Benefits Realisation Plan
4.2.3 Ownership of benefits delivery is assigned and accepted. | 7.4.1.3 Benefit Profiles
4.2.4 Benefits measurement approach and benefits delivery approach are reviewed periodically and confirmed or updated. | 7.4.4 Benefits Reviews
4.3 Evaluate attainment of expected benefits.
4.3.1 Deliverables from constituent projects are assessed in accordance with the benefits measurement approach. | 7.4.4 Benefits Reviews
4.3.2 Progress toward delivery of expected benefits is measured and reported to pertinent stakeholders. | 10.6.4 Delivering the Capability 16.7 Maintain alignment between programme bliueprint and business strategic objectives 16.14 End of Tranche review and close 18.4.4 Monitor and report benefits realization | Suggestion to remove 10.6.4 was not accepted, it is felt that this element contributed to the ability of the program manager to report on and track delivery as well as communicate to the stakeholders
4.3.3 Variances in delivery of expected benefits are addressed. | 12.4.5 Realiszing the Benefits (Quality) 18.2.2 Monitor Benefits Realization 18.3.5 Manage outcome achievement 18.4.4 Monitor and report benefits realization | Unclear comment - it appears that the existing mapping is repeated in column C -no action taken
Sustain Program Progress
5.1 Secure program funding.
5.1.1 Ongoing funding requirements are determined, documented, and communicated to pertinent stakeholders. | 9.2.2 Resource Management Strategy and Plan 10.1 Types of Programme Costs (table) 10.3.2 Costs A.4.23 - Resource Management Strategy | Suggestion from 5.1.4 was used to update this mapping - thank you!
5.1.2 Funding commitments are secured as needed. | 4.6.1 SRO - Secure the investment required | Unclear comment - it appears that the existing mapping is repeated in column C -no action taken
5.1.3 Funding issues are addressed. | 4.5.2 Sponsoring Group - Authorizing Funding for the Programme | Unclear comment - it appears that the existing mapping is repeated in column C -no action taken
5.1.4 Funding requirements are satisfied. |  | This suggestion was use to update the mapping to GAPPS 5.1.1 which requires funding requirements to be identified. A.4.23 doesn't discuss how the funding requirements are satisfied at the end so the suggestion has not been actioned here
5.2 Resource the program.
5.2.1 Program resource requirements are determined, documented, negotiated with, and communicated to pertinent stakeholders. | 9.2.2 Resource Management Strategy and Plan 14.6 Develop the Programme Preparation Plan
5.2.2 Program resources are acquired and coordinated across the program and its constituent projects. | 4.8.1 Responsibilities of the Programme Manager 9.2.2 Resource Management Strategy and Plan 11.1.1.3 Project Level
5.2.3 Program resource requirements are confirmed or updated in response to program refinements or changes. | 11.4 Managing issues in a Programme 11.6 Change Control 16.13 Prepare for Next Tranche 16.14 End of Tranche Review D2.2.3 Managing the Tranches | This suggestion has not been accepted as it doesn't specifically reference resource requirements althought it could be assumed to be included.
5.3 Measure, evaluate, and coordinate program progress.
5.3.1 Monitoring and control systems are established and maintained. | 5.3.5 Progress Monitoring
5.3.2 Monitoring and control systems are used to maintain momentum and support delivery of expected benefits. | 5.3.5 Progress Monitoring 10.5 Managing the Business Case (table 10.1) 17.6.1 Monitor and Control Progress
5.3.3 Performance of constituent projects and other program elements is reported to pertinent stakeholders. | 5.3.5 Progress Monitoring 9.5 Key Roles 16.3 Direct Work 17.6.1 Monitor and Control Progress
5.3.4 A sustainable pace is maintained. | 17.6.1 Monitor and Control Progress
5.4 Ensure relevant legal and regulatory requirements are addressed. |  | This is a Element title GAPPS does not map to the titles
5.4.1 Relevant legal and regulatory requirements are identified, documented, and communicated to pertinent stakeholders. | 8.2 Blueprint Design - POTI Model A.4.21 Quality Management Strategy includes specific standards, regulations etc., that ned to ve adhered to | Suggestion to remove 12.3.1.4 Risk Based was accepted
5.4.2 Potential for conflicts caused by legal and regulatory requirements are identified and addressed. | 12.3.1.4 Risk Based | Suggestion to add 12.3.1.4 and make it amber was accepted
5.4.3 Compliance policies, processes, and procedures are implemented. |  | Suggestion not accepted to add 17.6.1 as it does not discuss legal and regulatory compliance processes. Same for Table 3.3 suggested
5.4.4 Applicable legal and regulatory requirements are monitored for breaches and conflicts. |  | Suggestions not accepted as although there could be an implication that regulatory is covered by compliance in 12.3.2.3 it is not explicit enough
5.5 Anticipate and respond to changes.
5.5.1 Internal and external program contexts are monitored and evaluated for circumstances that may require changes. | 11.1.1.1 Strategic Level 11.1.1.2 Programme Level | Suggested additons of 11.1.1.1 and 11.1.1.2 have been accepted and the colour changed to amber. There was no discussion of evaluation and subsequent changes which would be required to make this green
5.5.2 Actual and potential changes are identified, documented, and evaluated. | 17.6.1 Monitor and Control Progress 11.1 Risk and Issue management 11.4 Managing Issues 11.4.2 Issue management Strategy 11.4.3 Issue register 11.6 Change Control | Suggestion to remove 17.6.1 Monitor and Control Progress has not been accepted as it is is relevant to the topic. And the colour has changed to green with the addition of 11.6 Change Control
5.5.3 Approved changes are implemented. | 11.5.3.5 Implement Step 11.6 Change Control | Suggestion to add 11.5.3.5 was accepted and changed to amber. And the colour was made green with the additional element of 11.6 change control
5.5.4 Changes and their implications are communicated to pertinent stakeholders. | 11.5.3.5 Implement Step 18.2.4 Communicate the Change | Suggestion to add 11.5.3.5 was accepted and changed to amber. And the colour was changed to green with the addition of 18.2.4
5.6 Manage program risks.
5.6.1 Risk management approach for the program and its constituent projects is documented, communicated, and agreed to by pertinent stakeholders. | 11.2.1 Risk Management Strategy 11.3.1 Communicate
5.6.2 Program risks are identified in consultation with pertinent stakeholders. | 11.2.6 Risk Register 11.3.1 Communicate
5.6.3 Program risks are analysed and prioritized, and risk responses are implemented as planned. | 11.2.8 Evaluating Risks 11.2.9 Risk Aggregation 11.3.3 Risk Management Cycle
5.6.4 Internal and external program contexts are monitored for circumstances that may affect program risks. | 11.2.11 Progress Reporting
Manage Organizational Change
6.1 Shape and sustain organizational change implementation approach.
6.1.1 The extent and nature of organizational change required in support of the program is evaluated and periodically re-evaluated. | 18.2.5 Assess Readiness for Change | Suggestions not accepted, GAPPS could not find any specific organisational project management capabilities within the suggested additions. If more detail could be provided on why and how these units relate to the specific competency of organsational change management we could re-visit this
6.1.2 Potential organizational change implementation approaches are identified and evaluated for applicability. | 18.3.1 Initiate Transition
6.1.3 The organizational change implementation approach is reviewed periodically and confirmed or modified to ensure support for expected benefits. | 18.3.2 Establish Support Arrangements | Suggestions not accepted, GAPPS could not find any specific organisational project management capabilities within the suggested additions. If more detail could be provided on why and how these units relate to the specific competency of organsational change management we could re-visit this
6.1.4 The organizational change implementation approach is coordinated with the program execution approach and accepted by pertinent stakeholders. | 18.3.3 Enact Transition
6.2 Advocate for change with stakeholders.
6.2.1 Approaches for stakeholder engagement in organizational change are devised and deployed. | 18.2.4 Communicate the Change | Suggestions not accepted, GAPPS could not find any specific organisational project management capabilities within the suggested additions. If more detail could be provided on why and how these units relate to the specific competency of organsational change management we could re-visit this Although all the suggested unit deal with communciation to stakeholders they do not specifically or explicitly relate themselves to organisational change only project progress which could imply change but not necessarily
6.2.2 Benefits of organizational change are articulated for pertinent stakeholders. | 18.2.4 Communicate the Change | as abobe
6.2.3 An organizational change communications plan is documented, maintained, and agreed to by pertinent stakeholders. | 18.2.4 Communicate the Change | as abobe
6.2.4 Organizational change communications plan is implemented and variances are addressed. | 18.2.4 Communicate the Change | as abobe
6.2.5 Resistance to change is monitored, evaluated, and addressed. | 18.2.5 Assess Readiness for Change | as abobe
6.3 Evaluate the effectiveness of the organizational change.
6.3.1 Methods for evaluating the effectiveness of the organizational change initiatives are identified, documented and agreed to by pertinent stakeholders. | 18.3.4 Review Transition
6.3.2 Selected evaluation methods are applied on an ongoing basis. | 18.3.4 Review Transition
6.3.3 Feedback is provided to pertinent stakeholders regarding progress of organizational change. | 18.3.4 Review Transition 18.3.5 Manage Outcome Achievement
6.3.4 Variances in attainment of desired organizational change are addressed. |  | No changes made - could you show us where MSP explicitly defines organsiational change as a benefit? We could not find this in the document in our search. If this is true then your rationale for treating Org change tracking under benefits realization is valid. All the other suggested additions like Change Control have not been accepted because they do not relate to Org Change Mgt rather Change Control
Direct the Management of Contracts
7.1 Shape and sustain contract management approach.
7.1.1 Contract management approach is devised, documented, kept current, and agreed to by pertinent stakeholders. | 9.2.2 Resource Management Strategy and Plan | Audit of contracts is a valid activity that is not covered in the GAPPS standard. This performance criteria is looking for the definition of a contract management strategy i.e how you plan to contract, what form and why. No action taken
7.1.2 Policies, processes, and procedures to support the contract management approach are developed, approved, maintained, and communicated to pertinent stakeholders. | 9.2.2 Resource Management Strategy and Plan 16.10 Procurement and Contracts
7.1.3 Risk management related to contracts is integrated with overall program risk management. |  | Suggestion not accepted because of the following points: 7.4.3 implies but is not explicit about the relationship with contracts 11.5.3.2 is about impacts to contracts from issues not the risks arising from contracts 12.2.2.2 touches on contract mangement but not the risk management component
7.2 Oversee and verify contract performance.
7.2.1 Contracts are approved in accordance with the contract management approach. | 9.2.2 Resource Management Strategey and Plan | There is no explicit mention of a contract management approach in MSP so this remains amber
7.2.2 Alignment of contractor performance with contract requirements is verified. | 16.10 Procurement and Contracts 9.2.2 Resource Management Strategey and Plan | as above
7.2.3 Resolution of contract variances is documented and verified. | 16.10 Procurement and Contracts 9.2.2 Resource Management Strategey and Plan | as above
7.2.4 Mechanisms to support effective communications, coordination, synergies, and integration of contracts with constituent projects in the program are implemented. |  | The suggested changes refer to generic communications that could include contracts but do not specifically address the topic. No action taken
7.2.5 Compliance with policies, processes, and procedures is monitored. |  | Agreed - Acknowleged that this is done by the Program Office in MSP. This standard can only map activities for the program manager role.
Engage in Collaborative Alliances
8.1 Cultivate collaborative alliances.
8.1.1 Opportunities for collaborative alliances are identified and evaluated.
8.1.2 Potential collaborators are identified and evaluated.
8.1.3 Relationships with potential collaborators are initiated, nuanced, and shaped. |  | Collaborative Alliances are a specific way of working that are not specifically addressed in MSP and so no action has been taken
8.2 Devise and elaborate collaborative agreements. |  | as above
8.2.1 A collaborative agreement approach is initiated, negotiated, documented, and accepted by the parties to each agreement. |  | as above
8.2.2 Each formal agreement is signed and regularly reviewed to ensure continuation of envisaged value and potential need for changes and additions.
8.2.3 Collaboration plans are developed for each agreement to support implementation.
8.3 Support the evolution of collaborative agreements.
8.3.1 Relationships with collaborators are monitored and nurtured to sustain commitment. |  | as above
8.3.2 Performance of all parties to an agreement is assessed against expected results and variances are addressed.
8.3.3 Changes to agreements are made as required
1.1 Purpose of this guide
2.2.7 Learning from Experience | 1.2 What is a programme
2.2.7 Learning from Experience | 1.3 What is programme management
2.2.7 Learning from Experience 16.13 Prepare for Next Tranche | 1.4 Why use programme management
3. Governance Themes Overview | 1.5 The Programme managment environment
4. Programme Organisation 4.1 Introduction 4.2 Programme Organisation Characteristics 4.3 Programme Leadership 4.4 Programme Structure | 1.6 Types of programmes
4.3 Programme Leadership | 1.7 Programme Impact
4.3 Programme Leadership 5.3 Developing and Maintaing the Vision Statement 5.5 Key roles | 1.8 When to use MSP
4.4 Programme Structure 4.16 Key Roles | 1.9 Best Management Practice Guidance
4.8.1 Responsibilities of the Programme Manager 9.2.2 Resource Management Strategy and Plan 11.1.1.3 Project Level | 1.10 Some MSP Terminology
4.8.2 Key Attributes of the Programme Manager | 1.11 How to Use this Guide
4.8.2 Key Attributes of the Programme Manager | 2.2.4 Focusing on the Benefits and the Threats to Them
4.8.2 Key Attributes of the Programme Manager | 2.2.6 Designing and Delivering a Coherent Capability
4.8.2 Key Attributes of the Programme Manager | 3.4 Illustration of the Relationship Between the Governance Themes and Transformational Flow
5.2 Characteristics of a good vision statement 5.3 Developing and Maintaing the Vision Statement | 4.5 Sponsoring Group
5.3 Developing and Maintaing the Vision Statement | 4.6 Senior Responsible Owner
5.3 Developing and Maintaing the Vision Statement | 4.7 Programme Board
5.3.5 Progress Monitoring | 4.9 Business Change Manager
5.3.5 Progress Monitoring 10.5 Managing the Business Case (table 10.1) 17.6.1 Monitor and Control Progress | 4.10 Business Change Team
5.3.5 Progress Monitoring 9.5 Key Roles 16.3 Direct Work 17.6.1 Monitor and Control Progress | 4.11 Programme Office
6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership | 4.12 Programme Assurance
6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership | 4.13 Additional Governance Roles
6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership | 4.15 Program Organisation within the transformational flow
6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership | 5.1 Introduction to Vision
6.1 Diagram 6.2 Nature of Stakeholder Engagement & the Role of Leadership | 5.4 Vision with the tranformational flow
6.8 Key Roles 9.5 Key Roles | 6.3 Leadership
6.8 Key Roles 9.5 Key Roles | 6.4 Business Change Management
7.4.1 Identify Benefits 18.4.1 Measure Benefits | 6.7 Leadership within the transformational flow
7.4.1 Identify Benefits 7.4.1.2 Benefits Management Strategy 18.4.1 Measure Benefits
7.4.1.3 Benefit Profiles
7.4.2.3 Benefits Realisation Plan
7.4.4 Benefits Reviews
7.4.4 Benefits Reviews
8.2 Blueprint Design 8.2.1 Future State 8.2.2 Current State & Gap Analysis 8.3 Designing the Blueprint Delivery 8.5 Key Roles
8.2 Blueprint Design 8.2.1 Future State 8.2.2 Current State & Gap Analysis 8.3 Designing the Blueprint Delivery 8.5 Key Roles
9.2 Programme Plan
9.2.2 Resource Management Strategy and Plan
9.2.2 Resource Management Strategy and Plan 10.1 Types of Programme Costs (table) 10.3.2 Costs
9.2.2 Resource Management Strategy and Plan 14.6 Develop the Programme Preparation Plan
9.2.2 Resource Management Strategy and Plan 16.10 Procurement and Contracts
10.2.1 Programme Mandate
10.2.2 Programme Brief 10.3 Contents of the Business Case 15.15 Develop and Confirm Programme Business Case
10.3 Contents of the Business Case
10.3 Contents of the Business Case
10.6.4 Delivering the Capability
10.6.4 Delivering the Capability
11.2.1 Risk Management Strategy 11.3.1 Communicate
11.2.11 Progress Reporting
11.2.6 Risk Register 11.3.1 Communicate
11.2.8 Evaluating Risks 11.2.9 Risk Aggregation 11.3.3 Risk Management Cycle
12.2.1 Quality and the Programme Management Principles 12.2.2.8 People Management
12.2.2.8 People Management
12.3.1.4 Risk Based
16.10 Procurement and Contracts
16.10 Procurement and Contracts
17.6.1 Monitor and Control Progress
17.6.1 Monitor and Control Progress
18.2.2 Monitor Benefits Realisation
18.2.2 Monitor Benefits Realisation
18.2.2 Monitor Benefits Realisation
18.2.4 Communicate the Change
18.2.4 Communicate the Change
18.2.4 Communicate the Change
18.2.4 Communicate the Change
18.2.5 Assess Readiness for Change
18.2.5 Assess Readiness for Change
18.3.1 Initiate Transition
18.3.2 Establish Support Arrangements
18.3.3 Enact Transition
18.3.4 Review Transition
18.3.4 Review Transition
18.3.4 Review Transition 18.3.5 Manage Outcome Achievement

## PMI
Mapping: PMI® The Standard for Program Management, 2nd Edition to GAPPS Program Manager Standards
The intent of the GAPPS mapping process is to use the GAPPS standards as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. The process used for mapping of standards against the GAPPS standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS Working Session 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS Working Session 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the GAPPS standards has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. As the GAPPS framework is intended to be used to assess threshold competency — demonstration of the ability to do something at a standard considered acceptable in the workplace - it is expected that the coverage of other standards is most likely to be considerably broader than that of the GAPPS standard. Topics or activities that are included in other standards, but not included in the GAPPS standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the GAPPS standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case the ICB® v3.0) maps against the GAPPS standard. This mapping has been reviewed by PMI
LEGEND:
NO Mapping
Partial/Some Mapping
Full Mapping
GAPPS (2011) A Framework for Performance Based Competency Standards for Program Manager | PMI® The Standard for Program Management, 2nd Edition
Provide Leadership for the Program
1.1 Promote the program vision.
1.1.1 Alignment of the program vision with the vision, mission, principles, and values of the sponsoring organization is maintained. | 2.2.3 Program Setup
1.1.2 Engagement with the program vision is stimulated through ongoing review, monitoring, communications, and negotiations with pertinent stakeholders.
1.1.3 Commitment to the program vision is demonstrated by the program manager. | 15.1 Plan and Establish Program Governance Structure
1.2 Build an environment of confidence and trust within the program.
1.2.1 Stakeholders are treated fairly and equitably. | 3.5.5 Engage Program Stakeholders
1.2.2 Open discussion is encouraged and facilitated.
1.2.3 Differences are managed constructively. | 3.5.5 Engage Program Stakeholders
1.2.4 Issues and concerns are attended to in a timely manner.
1.2.5 Interpersonal and leadership styles are chosen and applied based on the circumstances. | 1 Introduction
1.2.6 Personal commitments are realistic and honoured.
1.3 Embed socially responsible practice into the program.
1.3.1 Expectations for socially responsible practice are made explicit and communicated to constituent projects and other pertinent stakeholders.
1.3.2 Policies and procedures are designed to allow individuals to safely report breaches of socially responsible practice without fear of retaliation.
1.3.3 Threats to socially responsible practice within the program are identified and addressed.
1.4 Develop the potential of program staff.
1.4.1 Individual behavioural expectations for constituent project managers are established.
1.4.2 Individual program roles are defined, documented, communicated, assigned, and agreed to. | 15.1 Plan and Establish Program Governance Structure
1.4.3 Desirable behaviours are encouraged, and undesirable behaviours are discouraged.
1.5 Support a learning environment.
1.5.1 Program planning and program plan implementation are viewed as a learning process.
1.5.2 Errors, mistakes, and expressed concerns are treated as learning opportunities.
1.5.3 Plans for identifying, capturing, disseminating, and exchanging knowledge are developed and maintained. | 5.8.3 Close Program: Outputs
1.5.4 Program knowledge is identified, captured, disseminated, and exchanged as planned. | 10.2.2 Distribute Information: Tools and Techniques
1.5.5 Reflection on and review of practice is encouraged as a basis for learning. | 2.2.5 Program Closure
Facilitate Stakeholder Engagement
2.1 Communicate effectively with stakeholders.
2.1.1 Program stakeholders and their communication needs are identified and documented. | 2.2.2 Program Initiation 3.4.4 Identify Program Stakeholders 3.4.16 Plan Communication 10.1 Plan Communication 14.2 Identify Program Stakeholders
2.1.2 Communication approaches are agreed to by pertinent stakeholders. | 3.4.16 Plan Communication 10.1 Plan Communication
2.1.3 Information is shared as planned, and variances are identified and addressed. | 3.5.6 Distribute Information 3.6.5 Manage Program Stakeholder Expectations 10.2 Distribute Information 14.4 Manage Program Stakeholder Expectations
2.1.4 Communication interfaces among constituent projects are monitored. | 3.5.4 Manage Component Interfaces 5.7 Manage Component Interfaces
2.2 Cultivate stakeholder commitment.
2.2.1 Interests and expectations of pertinent stakeholders are investigated, documented, and considered when making program decisions. | 14.3 Engage Program Stakeholders
2.2.2 Approaches to influence ongoing stakeholder commitment are developed and implemented. | 3.4.15 Plan Program Stakeholder Management 14.1 Plan Program Stakeholder Management
2.2.3 Actions are taken to accommodate differing stakeholder interests and expectations. | 3.6.5 Manage Program Stakeholder Expectations 14.4 Manage Program Stakeholder Expectations
2.2.4 Evolving stakeholder interests and expectations are shared across the program. | 3.5.5 Engage Program Stakeholders 14.3 Engage Program Stakeholders
Craft the Program
3.1 Envision the desired future state.
3.1.1 Description of the desired future state is defined and agreed to by pertinent stakeholders. | 2.2.2 Program Initiation 3.4.7 Develop Program Requirements 5.3 Develop Program Requirements
3.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the desired future state. | 1.7 Program-External Factors
3.1.3 The description of the desired future state is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits.
3.2 Shape and sustain the program execution approach.
3.2.1 Gaps between the current state and the desired future state are defined and agreed to by pertinent stakeholders. | 2.3.1 Delivering and Managing Benefits
3.2.2 Changes needed to move from the current state to the desired future state are defined and agreed to by pertinent stakeholders. | 3.3 Initiating Process Group 5.1 Plan Program Scope
3.2.3 A program execution approach based on changes needed is defined and agreed to by pertinent stakeholders. | 3.4.5 Develop Program Management Plan 4.2 Develop Program Management Plan
3.2.4 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program execution approach. | 1.7 Program-External Factors
3.2.5 The program execution approach is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 2.3.1 Delivering and Managing Benefits 5.8 Monitor and Control Program Scope
3.3 Shape and sustain the program’s business case.
3.3.1 A business case for both the desired future state and the program execution approach is defined, documented, and approved by pertinent stakeholders. | 2.2.1 Pre-Program Preparations
3.3.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program’s business case. | 1.7 Program-External Factors
3.3.3 The program’s business case is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 2.3.1 Delivering and Managing Benefits
3.4 Shape and sustain program governance.
3.4.1 Program organization is defined, maintained, refreshed, and agreed by the sponsoring organization.
3.4.2 Program boundaries and governance structures are designed to exploit synergies within the sponsoring organization. | 2.1.4 Program Governance across the Life Cycle
3.4.3 Policies, processes, and procedures to support the management of the program are identified/devised and communicated to pertinent stakeholders. | 3.4 Planning Process Group
Orchestrate Attainment of Benefits
4.1 Identify benefits and trade-offs.
4.1.1 Expected short- and long-term benefits and trade-offs are defined and communicated to pertinent stakeholders. | 2.2.2 Program Initiation
4.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the expected benefits. | 1.7 Program-External Factors
4.1.3 Expected benefits and trade-offs are periodically reviewed and confirmed or updated. | 2.3.1 Delivering and Managing Benefits
4.2 Shape and sustain benefits delivery approach.
4.2.1 Benefits measurement approach is defined and agreed to by pertinent stakeholders. | 2.3.1 Delivering and Managing Benefits 5.2 Define Program Goals and Objectives
4.2.2 Benefits delivery approach is devised and agreed to by pertinent stakeholders. | 2.3.1 Delivering and Managing Benefits 5.2 Define Program Goals and Objectives
4.2.3 Ownership of benefits delivery is assigned and accepted. | 2.3.3 Benefits Sustainment
4.2.4 Benefits measurement approach and benefits delivery approach are reviewed periodically and confirmed or updated.
4.3 Evaluate attainment of expected benefits.
4.3.1 Deliverables from constituent projects are assessed in accordance with the benefits measurement approach. | 4.6 Monitor and Control Program Performance 10.3 Report Program Performance
4.3.2 Progress toward delivery of expected benefits is measured and reported to pertinent stakeholders. | 3.6.12 Manage Program Benefits 15.6 Manage Program Benefits
4.3.3 Variances in delivery of expected benefits are addressed. | 10.3.3 Report Program Performance 15.6 Manage Program Benefits
Sustain Program Progress
5.1 Secure program funding.
5.1.1 Ongoing funding requirements are determined, documented, and communicated to pertinent stakeholders. | 3.4.13 Budget Program Costs 13 Program Financial Management
5.1.2 Funding commitments are secured as needed. | 13 Program Financial Management
5.1.3 Funding issues are addressed. | 13 Program Financial Management
5.1.4 Funder requirements are satisfied.
5.2 Resource the program.
5.2.1 Program resource requirements are determined, documented, negotiated with, and communicated to pertinent stakeholders. | 2.2.2 Program Initiation
5.2.2 Program resources are acquired and coordinated across the program and its constituent projects. | 3.5.2 Manage Program Resources
5.2.3 Program resource requirements are confirmed or updated in response to program refinements or changes. | 3.5.2 Manage Program Resources
5.3 Measure, evaluate, and coordinate program progress.
5.3.1 Monitoring and control systems are established and maintained. | 3.6 Monitoring and Controlling Process Group
5.3.2 Monitoring and control systems are used to maintain momentum and support delivery of expected benefits. | 3.1 Common Program Management Process Interactions 3.6.1 Monitor and Control Program Performance
5.3.3 Performance of constituent projects and other program elements is reported to pertinent stakeholders. | 3.1 Common Program Management Process Interactions
5.3.4 A sustainable pace is maintained.
5.4 Ensure relevant legal and regulatory requirements are addressed.
5.4.1 Relevant legal and regulatory requirements are identified, documented, and communicated to pertinent stakeholders. | 5.3 Develop Program Requirements 11.5 Monitor and Control Program Risks 12.1 Plan Program Procurements
5.4.2 Potential for conflicts caused by legal and regulatory requirements are identified and addressed. | 11.5 Monitor and Control Program Risks
5.4.3 Compliance policies, processes, and procedures are implemented. | 3.4 .17 Plan for Audits 15.2 Plan for Audits 3.6 Monitoring and Controlling Process Group 4.5 Manage Program Resources
5.4.4 Applicable legal and regulatory requirements are monitored for breaches and conflicts. | 11.5 Monitor and Control Program Risks
5.5 Anticipate and respond to changes.
5.5.1 Internal and external program contexts are monitored and evaluated for circumstances that may require changes. | 1.7 Program-External Factors
5.5.2 Actual and potential changes are identified, documented, and evaluated. | 10
5.5.3 Approved changes are implemented. | 3.5.8 Approve Component Initiation 3.6.2 Monitor and Control Program Scope 3.6.9 Monitor and Control Program Changes 15.7 Monitor and Control Program Changes 5.8 Monitor and Control Program Scope
5.5.4 Changes and their implications are communicated to pertinent stakeholders. | 3.6.2 Monitor and Control Program Scope 5.8 Monitor and Control Program Scope
5.6 Manage program risks.
5.6.1 Risk management approach for the program and its constituent projects is documented, communicated, and agreed to by pertinent stakeholders. | 3.4 Planning Process Group 11.1 Plan Program Risk Management
5.6.2 Program risks are identified in consultation with pertinent stakeholders. | 2.2.2 Program Initiation 3.4.20 Identify Program Risks 11.2 Identify Program Risks
5.6.3 Program risks are analysed and prioritized, and risk responses are implemented as planned. | 3.4.21 Analyse Program Risks 3.4.22 Plan Program Risk Responses 3.6.6 Monitor and Control Program Risks 11.3 Analyse Program Risks 11.4 Plan Program Risk Responses 11.5 Monitor and Control Program Risks
5.6.4 Internal and external program contexts are monitored for circumstances that may affect program risks. | 1.7 Program-External Factors
Manage Organizational Change
6.1 Shape and sustain organizational change implementation approach.
6.1.1 The extent and nature of organizational change required in support of the program is evaluated and periodically re-evaluated.
6.1.2 Potential organizational change implementation approaches are identified and evaluated for applicability.
6.1.3 The organizational change implementation approach is reviewed periodically and confirmed or modified to ensure support for expected benefits.
6.1.4 The organizational change implementation approach is coordinated with the program execution approach and accepted by pertinent stakeholders.
6.2 Advocate for change with stakeholders.
6.2.1 Approaches for stakeholder engagement in organizational change are devised and deployed.
6.2.2 Benefits of organizational change are articulated for pertinent stakeholders.
6.2.3 An organizational change communications plan is documented, maintained, and agreed to by pertinent stakeholders.
6.2.4 Organizational change communications plan is implemented and variances are addressed.
6.2.5 Resistance to change is monitored, evaluated, and addressed.
6.3 Evaluate the effectiveness of the organizational change.
6.3.1 Methods for evaluating the effectiveness of the organizational change initiatives are identified, documented and agreed to by pertinent stakeholders.
6.3.2 Selected evaluation methods are applied on an ongoing basis.
6.3.3 Feedback is provided to pertinent stakeholders regarding progress of organizational change.
6.3.4 Variances in attainment of desired organizational change are addressed.
Direct the Management of Contracts
7.1 Shape and sustain contract management approach.
7.1.1 Contract management approach is devised, documented, kept current, and agreed to by pertinent stakeholders. | 3.4.14 Plan Program Procurements 3.6.7 Administer Program Procurements 12.1 Plan Program Procurements 12.3 Administer Program Procurements
7.1.2 Policies, processes, and procedures to support the contract management approach are developed, approved, maintained, and communicated to pertinent stakeholders. | 3.5.7 Conduct Program Procurements 12.2 Conduct Program Procurements
7.1.3 Risk management related to contracts is integrated with overall program risk management. | 11.5 Monitor and Control Program Risks
7.2 Oversee and verify contract performance.
7.2.1 Contracts are approved in accordance with the contract management approach. | 12.2 Conduct Program Procurements 12.1 Plan Program Procurements
7.2.2 Alignment of contractor performance with contract requirements is verified. | 12.3 Administer Program Procurements
7.2.3 Resolution of contract variances is documented and verified. | 12.3 Administer Program Procurements
7.2.4 Mechanisms to support effective communications, coordination, synergies, and integration of contracts with constituent projects in the program are implemented.
7.2.5 Compliance with policies, processes, and procedures is monitored. | 3.4 .17 Plan for Audits 15.2 Plan for Audits 3.6 Monitoring and Controlling Process Group 4.5 Manage Program Resources
Engage in Collaborative Alliances
8.1 Cultivate collaborative alliances.
8.1.1 Opportunities for collaborative alliances are identified and evaluated.
8.1.2 Potential collaborators are identified and evaluated.
8.1.3 Relationships with potential collaborators are initiated, nuanced, and shaped.
8.2 Devise and elaborate collaborative agreements.
8.2.1 A collaborative agreement approach is initiated, negotiated, documented, and accepted by the parties to each agreement.
8.2.2 Each formal agreement is signed and regularly reviewed to ensure continuation of envisaged value and potential need for changes and additions.
8.2.3 Collaboration plans are developed for each agreement to support implementation.
8.3 Support the evolution of collaborative agreements.
8.3.1 Relationships with collaborators are monitored and nurtured to sustain commitment.
8.3.2 Performance of all parties to an agreement is assessed against expected results and variances are addressed.
8.3.3 Changes to agreements are made as required
1.1 Purpose of the Standard for Program Management
1.2 What is a program?
1.3 What is Program Management?
1.4 Relationships among Project, Program and Portfolio
1.5 Program Management Office
1.6 Role of the Program Manager
2.1.1 Characteristics of the Program Life Cycle
2.1.2 Relationship to a Product´s Life Cycle
2.1.3 Program Life Cycle and Benefits Management
2.2.4 Delivery of Program Benefits
2.3.2 Organizational Differences
3.2 Program Management Process Groups
3.3.1 Initiate Program
3.3.2 Establish Program Finacial Framework
3.4.1 Plan Program Scope
3.4.2 Define Program Goals and Objectives
3.4.3 Plan and Establish Program Governance Structure
3.4.5 Develop Program Management Plan
3.4.6 Develop Program Infrastructure
3.4.8 Develop Program Architecture
3.4.9 Develop Program WBS
3.4.10 Develop Program Schedule
3.4.11 Develop Program Financial Plan
3.4.12 Estimate Program Costs
3.4.13 Budget Program Costs
3.4.18 Plan Quality
3.4.19 Plan Program Risk Management
3.5.1 Direct and Manage Program Execution
3.5.3 Manage Program Architecture
3.6.3 Monitor and Control Program Schedule
3.6.4 Monitor and Control Program Financials
3.6.8 Manage Program Issues
3.6.11 Provide Governance Oversight
3.7 Closing Process Group
4.1 Initiate Program
4.3 Develop Program Infrastructure
4.4 Direct and Manage Program Execution
4.7 Manage Program Issues
4.8 Close Program
5.4 Develop Program Architecture
5.5 Develop Program WBS
5.6 Manage Program Architecture
6.1 Develop Program Schedule
6.2 Monitor and Control Program Schedule
| 7 Program Cost Management | *
| 8 Program Quality Management | *
| 9 Program Human Resource Management | *
12.4 Close Program Procurements
15.3 Plan Program Quality
15.4 Approve Component Initiation
15.5 Provide Governance Oversight
15.8 Approve Component Transition
* refers to another standard

## P2M
Mapping: P2M to GAPPS Program Manager Standards
The intent of the GAPPS mapping process is to use the GAPPS standards as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. Therefore, this is a mapping of the COVERAGE only of the P2M Heading and Sub-heading Levl. All of these have been mapped against the GAPPS standards. The process used for mapping of standards against the GAPPS standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS Working Session 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS Working Session 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the GAPPS standards has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. As the GAPPS framework is intended to be used to assess threshold competency — demonstration of the ability to do something at a standard considered acceptable in the workplace - it is expected that the coverage of other standards is most likely to be considerably broader than that of the GAPPS standard. Topics or activities that are included in other standards, but not included in the GAPPS standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the GAPPS standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case P2M) maps against the GAPPS standard.
LEGEND:
NO Mapping
Partial/Some Mapping
Full Mapping
GAPPS (2011) A Framework for Performance Based Competency Standards for Program Manager | P2M (Program and Project Management for Enterprise Innovation) 3rd Edition
Provide Leadership for the Program PgM 01
1.1 Promote the program vision.
1.1.1 Alignment of the program vision with the vision, mission, principles, and values of the sponsoring organization is maintained. | 2-2, Exhibit 2-0-1 Structure of program management (redisplay) 2-2, 1 Mission Profiling 2-2, 3 Integration Management of Program Implementation
1.1.2 Engagement with the program vision is stimulated through ongoing review, monitoring, communications, and negotiations with pertinent stakeholders. | 4-1 2-3, Business Management Cycle and Program Management Processes, 3 Program and Project Governance 2-2, Exhibit 2-2-16 Processes for establishing the organizational strategy 2-2, Exhibit 2-2-19 Object and main operation of integration management of program implementation
1.1.3 Commitment to the program vision is demonstrated by the program manager. | 2-2, 3-1 Process for the Integration Management of Program Implementation 2-2, Exhibit 2-2-18 Summary example of processes for integration management of program implementation 2-2, Exhibit 2-2-19 Object and main operation of integration management of program implementation
1.2 Build an environment of confidence and trust within the program.
1.2.1 Stakeholders are treated fairly and equitably. | 3-3, 3.Stakeholder Management
1.2.2 Open discussion is encouraged and facilitated. | 2-2, 4 Relationship Management 3-3, 3 Stakeholder Management 3-11, 1 Overview
1.2.3 Differences are managed constructively. | 2-2, 4 Relationship Management 3-3, 3 Stakeholder Management , (Conflict Management)
1.2.4 Issues and concerns are attended to in a timely manner. | 3-11, Communication Management, 2-3 Establishment of means of communication
1.2.5 Interpersonal and leadership styles are chosen and applied based on the circumstances. | 1-5, 1 Capability for P2M 3-1, 5 Requirements of Project Management 6-1, 2 Ability Elements and Evaluation Criteria in Capability
1.2.6 Personal commitments are realistic and honored. | not shown specifically
1.3 Embed socially responsible practice into the program.
1.3.1 Expectations for socially responsible practice are made explicit and communicated to constituent projects and other pertinent stakeholders. | 1-5, 1 Qualifications for Program and Project Managers (1) Due Diligence 6-1, 1 Capability Requiredfor a Manager 6-1, 1-4 (4) Basic Attitude
1.3.2 Policies and procedures are designed to allow individuals to safely report breaches of socially responsible practice without fear of retaliation. | 1-5, 1 Qualifications for Program and Project Managers (1) Due Diligence 6-1, 1 Capability Requiredfor a Manager 6-1, 1-4 (4) Basic Attitude
1.3.3 Threats to socially responsible practice within the program are identified and addressed. | 1-5, 1 Qualifications for Program and Project Managers (1) Due Diligence 6-1, 1 Capability Requiredfor a Manager 6-1, 1-4 (4) Basic Attitude
1.4 Develop the potential of program staff.
1.4.1 Individual behavioral expectations for constituent project managers are established. | 6-1 Capability of Manager for Practicing P2M 6-1, 4 Experiential Learning Process for Honing Capability
1.4.2 Individual program roles are defined, documented, communicated, assigned, and agreed to. | not shown specifically
1.4.3 Desirable behaviors are encouraged, and undesirable behaviors are discouraged. | 6-1 Capability of Manager for Practicing P2M 6-1, 4 Experiential Learning Process for Honing Capability
1.5 Support a learning environment.
1.5.1 Program planning and program plan implementation are viewed as a learning process. | 2-4, 2-1(3) Learning as an organization 6-2, 3 Empowerment for Human Resources Management
1.5.2 Errors, mistakes, and expressed concerns are treated as learning opportunities. | 2-4, 2-1(3) Learning as an organization
1.5.3 Plans for identifying, capturing, disseminating, and exchanging knowledge are developed and maintained. | 3-5, 7-4 Example of the Accumulation of Resources (1) Lessons Learned
1.5.4 Program knowledge is identified, captured, disseminated, and exchanged as planned | 3-5, 7-4 Example of the Accumulation of Resources (1) Lessons Learned 2-4, 2-1(3) Learning as an organization
1.5.5 Reflection on and review of practice is encouraged as a basis for learning. | 3-5, 7-4 Example of the Accumulation of Resources (1) Lessons Learned (2) Accumulation of project documents 2-4, 2-1(3) Learning as an organization
Facilitate Stakeholder Engagement PgM 02
2.1 Communicate effectively with stakeholders.
2.1.1 Program stakeholders and their communication needs are identified and documented. | 3-3, 3 Stakeholder Management
2.1.2 Communication approaches are agreed to by pertinent stakeholders. | 3-3, 3 Stakeholder Management, 3-11 Communication Management, 1-3 Practical Guidelines
2.1.3 Information is shared as planned, and variances are identified and addressed. | 3-3 Stakeholder Management, 3-11, 4 Communication Management
2.1.4 Communication interfaces among constituent projects are monitored. | 3-11, Communication Management 3-11, Exhibit 3-11-1 Overview of Communication Management 3-11, Exhibit 3-11-3 Example of a Communication List
2.2 Cultivate stakeholder commitment.
2.2.1 Interests and expectations of pertinent stakeholders are investigated, documented, and considered when making program decisions. | 3-3, 3 Stakeholder Management Exhibit 3-3-1 Outline of stakeholder management
2.2.2 Approaches to influence ongoing stakeholder commitment are developed and implemented. | 3-3, 3 Stakeholder Management
2.2.3 Actions are taken to accommodate differing stakeholder interests and expectations. | 3-3, 3 Stakeholder Management
2.2.4 Evolving stakeholder interests and expectations are shared across the program. | 3-3, 3 Stakeholder Management
Craft the Program PgM 03
3.1 Envision the desired future state.
3.1.1 Description of the desired future state is defined and agreed to by pertinent stakeholders. | 2-1, 3-2-1, 2-2, 1-1 Mission Profiling 4-0, 4 Programs and Strategies
3.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the desired future state. | 2-3, 1-2 Risks in the Program 2-2, 3-1-2 Goal Management of Program Implementation
3.1.3 The description of the desired future state is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 2-2, 3-1-2 Goal Management of Program Implementation (3) Program Change Management
3.2 Shape and sustain the program execution approach.
3.2.1 Gaps between the current state and the desired future state are defined and agreed to by pertinent stakeholders. | 2-2, 3-1-2 Goal Management of Program Implementation (3) Program Change Management
3.2.2 Changes needed to move from the current state to the desired future state are defined and agreed to by pertinent stakeholders. | 2-2, 3-1-2 Goal Management of Program Implementation (3) Program Change Management
3.2.3 A program execution approach based on changes needed is defined and agreed to by pertinent stakeholders. | 2-2, 3-1-2 Goal Management of Program Implementation (3) Program Change Management
3.2.4 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program execution approach. | 2-2, 3-1-2 Goal Management of Program Implementation 2-2, Exhibit 2-2-24: Examples of factors for program changes 2-2, Exhibit 2-2-25: Major Perspectives in of Multiproject Management
3.2.5 The program execution approach is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 2-2, 3-1 Process for the Integration Management of Program Implementation
3.3 Shape and sustain the program’s business case.
3.3.1 A business case for both the desired future state and the program execution approach is defined, documented, and approved by pertinent stakeholders. | 2-2, Exhibit 2-2-12: Viewpoints about the Lifecycles of the project models 2-2, 2-3 Program Concept Plan
3.3.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the program’s business case. | 2-2, 3-1-2 Goal Management of Program Implementation (3) Program Change Management
3.3.3 The program’s business case is reviewed periodically and confirmed or updated to maintain alignment with the expected benefits. | 2-2, 3-1-2 Goal Management of Program Implementation
3.4 Shape and sustain program governance.
3.4.1 Program organization is defined, maintained, refreshed, and agreed by the sponsoring organization. | 2-1, 5 Program Organization 5-3 Common View of a Program
3.4.2 Program boundaries and governance structures are designed to exploit synergies within the sponsoring organization. | 2-2, 3-1-1 Launching of Program Implementation (5) System for Total Optimization
3.4.3 Policies, processes, and procedures to support the management of the program are identified/devised and communicated to pertinent stakeholders. | 2-2, 2-3 Program Concept Plan
Orchestrate Attainment of Benefits PgM 04
4.1 Identify benefits and trade-offs.
4.1.1 Expected short- and long-term benefits and trade-offs are defined and communicated to pertinent stakeholders. | 2-0, Exhibit 2-0-1 Structure of program management (redisplay) 2-2, Exhibit 2-2-13 Example of a concept plan
4.1.2 Internal and external program contexts are monitored and evaluated for circumstances that may require changes to the expected benefits. | 2-2, 3-1-2 Goal Management of Program Implementation (3) Program Change Management
4.1.3 Expected benefits and trade-offs are periodically reviewed and confirmed or updated. | 2-2, 3-1-2 Goal Management of Program Implementation
4.2 Shape and sustain benefits delivery approach.
4.2.1 Benefits measurement approach is defined and agreed to by pertinent stakeholders. | not shown specifically
4.2.2 Benefits delivery approach is devised and agreed to by pertinent stakeholders. | not shown specifically
4.2.3 Ownership of benefits delivery is assigned and accepted. | not shown specifically
4.2.4 Benefits measurement approach and benefits delivery approach are reviewed periodically and confirmed or updated. | not shown specifically
4.3 Evaluate attainment of expected benefits.
4.3.1 Deliverables from constituent projects are assessed in accordance with the benefits measurement approach. | 2-2, Exhibit 2-2-23: Main program monitoring targets
4.3.2 Progress toward delivery of expected benefits is measured and reported to pertinent stakeholders. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring and Control
4.3.3 Variances in delivery of expected benefits are addressed. | not shown specifically
Sustain Program Progress PgM 05
5.1 Secure program funding.
5.1.1 Ongoing funding requirements are determined, documented, and communicated to pertinent stakeholders. | not shown specifically
5.1.2 Funding commitments are secured as needed. | not shown specifically
5.1.3 Funding issues are addressed. | not shown specifically
5.1.4 Funder requirements are satisfied. | not shown specifically
5.2 Resource the program.
5.2.1 Program resource requirements are determined, documented, negotiated with, and communicated to pertinent stakeholders. | 2-1, 5-1 Establishment of Program Organization 3-3, 3-1-1 Purpose of Stakeholder Management
5.2.2 Program resources are acquired and coordinated across the program and its constituent projects. | 2-1, 5-1 Establishment of Program Organization
5.2.3 Program resource requirements are confirmed or updated in response to program refinements or changes. | 2-1, 5-1 Establishment of Program Organization
5.3 Measure, evaluate, and coordinate program progress.
5.3.1 Monitoring and control systems are established and maintained. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring
5.3.2 Monitoring and control systems are used to maintain momentum and support delivery of expected benefits. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring
5.3.3 Performance of constituent projects and other program elements is reported to pertinent stakeholders. | not shown specifically
5.3.4 A sustainable pace is maintained. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring and Control 2) Acceleration of Implementation
5.4 Ensure relevant legal and regulatory requirements are addressed.
5.4.1 Relevant legal and regulatory requirements are identified, documented, and communicated to pertinent stakeholders. | not shown specifically
5.4.2 Potential for conflicts caused by legal and regulatory requirements are identified and addressed. | not shown specifically
5.4.3 Compliance policies, processes, and procedures are implemented. | not shown specifically
5.4.4 Applicable legal and regulatory requirements are monitored for breaches and conflicts. | not shown specifically
5.5 Anticipate and respond to changes.
5.5.1 Internal and external program contexts are monitored and evaluated for circumstances that may require changes. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring and Control (3) Program Change Management
5.5.2 Actual and potential changes are identified, documented, and evaluated. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring and Control (3) Program Change Management
5.5.3 Approved changes are implemented. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring and Control (3) Program Change Management
5.5.4 Changes and their implications are communicated to pertinent stakeholders. | 2-2, 3-1-2 Goal Management of Program Implementation (1) Monitoring and Control (3) Program Change Management 3-2, 6 Change control 3-4, 5 Scope Change Control
5.6 Manage program risks.
5.6.1 Risk management approach for the program and its constituent projects is documented, communicated, and agreed to by pertinent stakeholders. | 2-3, 3 Program Risk Management 3-8 Risk Management
5.6.2 Program risks are identified in consultation with pertinent stakeholders. | not shown specifically
5.6.3 Program risks are analysed and prioritized, and risk responses are implemented as planned. | 2-3, 3 Program Risk Management
5.6.4 Internal and external program contexts are monitored for circumstances that may affect program risks. | 2-3, 3 Program Risk Management
Manage Organizational Change PgM 06
6.1 Shape and sustain organizational change implementation approach.
6.1.1 The extent and nature of organizational change required in support of the program is evaluated and periodically re-evaluated. | 2-1, 5-1 Establishment of the Program Organization 2-2, 3-1-2 Goal Management of Program Impementation
6.1.2 Potential organizational change implementation approaches are identified and evaluated for applicability. | 2-1, 5-1 Establishment of the Program Organization 2-2, 3-1-2 Goal Management of Program Impementation
6.1.3 The organizational change implementation approach is reviewed periodically and confirmed or modified to ensure support for expected benefits. | 2-1, 5-1 Establishment of the Program Organization 2-2, 3-1-2 Goal Management of Program Impementation
6.1.4 The organizational change implementation approach is coordinated with the program execution approach and accepted by pertinent stakeholders. | 2-1, 5-1 Establishment of the Program Organization 2-2, 3-1-2 Goal Management of Program Impementation
6.2 Advocate for change with stakeholders.
6.2.1 Approaches for stakeholder engagement in organizational change are devised and deployed. | 2-2, 3-1-1 Launching of Program Implementation 2-2, 4 Relationship Management
6.2.2 Benefits of organizational change are articulated for pertinent stakeholders. | 2-2, 3-1-1 Launching of Program Implementation 2-2, 4 Relationship Management
6.2.3 An organizational change communications plan is documented, maintained, and agreed to by pertinent stakeholders. | 2-2, 3-1-1 Launching of Program Implementation 2-2, 4 Relationship Management
6.2.4 Organizational change communications plan is implemented and variances are addressed. | 2-2, 3-1-1 Launching of Program Implementation 2-2, 4 Relationship Management
6.2.5 Resistance to change is monitored, evaluated, and addressed. | 2-2, 3-1-1 Launching of Program Implementation 2-2, 4 Relationship Management
6.3 Evaluate the effectiveness of the organizational change. ここは赤では？
6.3.1 Methods for evaluating the effectiveness of the organizational change initiatives are identified, documented and agreed to by pertinent stakeholders. | 2-4, 2-6 Designing Value assessment
6.3.2 Selected evaluation methods are applied on an ongoing basis. | 2-4, 2-6 Designing Value assessment
6.3.3 Feedback is provided to pertinent stakeholders regarding progress of organizational change. | 2-4, 2-6 Designing Value assessment
6.3.4 Variances in attainment of desired organizational change are addressed. | 2-4, 2-6 Designing Value assessment
Direct the Management of Contracts PgM 07
7.1 Shape and sustain contract management approach.
7.1.1 Contract management approach is devised, documented, kept current, and agreed to by pertinent stakeholders. | 2-3, Exhibit 2-3-8 Risks and Solutions at the Strategic Level 3-10, 4-2 Procurement Control (1) Contract management
7.1.2 Policies, processes, and procedures to support the contract management approach are developed, approved, maintained, and communicated to pertinent stakeholders. | not shown specifically
7.1.3 Risk management related to contracts is integrated with overall program risk management. | 2-3, 3-3 Characteristics of Projects and Program Risk Management 2-3, Exhibit 2-3-9 Program Risk Management and Project Risk Management
7.2 Oversee and verify contract performance.
7.2.1 Contracts are approved in accordance with the contract management approach. | not shown specifically
7.2.2 Alignment of contractor performance with contract requirements is verified. | 3-10, 4-1 Basic Information for Procurement Control (2) Progress/performance reports
7.2.3 Resolution of contract variances is documented and verified. | not shown specifically
7.2.4 Mechanisms to support effective communications, coordination, synergies, and integration of contracts with constituent projects in the program are implemented. | not shown specifically
7.2.5 Compliance with policies, processes, and procedures is monitored. | not shown specifically
Engage in Collaborative Alliances PgM 08
8.1 Cultivate collaborative alliances.
8.1.1 Opportunities for collaborative alliances are identified and evaluated. | 4-2, 5 Open Innovation 4-3, 7-1 Types and Patterns of Alliance
8.1.2 Potential collaborators are identified and evaluated. | 4-3, 7-1 Types and Patterns of Alliance
8.1.3 Relationships with potential collaborators are initiated, nuanced, and shaped. | 4-3, 7-1 Types and Patterns of Alliance
8.2 Devise and elaborate collaborative agreements.
8.2.1 A collaborative agreement approach is initiated, negotiated, documented, and accepted by the parties to each agreement. | 4-3, 7-2 Contracts that Bind Alliance
8.2.2 Each formal agreement is signed and regularly reviewed to ensure continuation of envisaged value and potential need for changes and additions. | 4-3, 7-2 Contracts that Bind Alliance 4-3, 7-4 Risks and Points of Attention in Alliance Building
8.2.3 Collaboration plans are developed for each agreement to support implementation. | 4-3, 7-3 Sharing of Scope and Project Formation
8.3 Support the evolution of collaborative agreements.
8.3.1 Relationships with collaborators are monitored and nurtured to sustain commitment. | 4-3, 7-4 Risks and Points of Attention in Alliance Building
8.3.2 Performance of all parties to an agreement is assessed against expected results and variances are addressed. | 4-3, 7-4 Risks and Points of Attention in Alliance Building
8.3.3 Changes to agreements are made as required | 4-3, 7-2 Contracts that Bind Alliance
Overs
2-1, 1. Organization´s Strategy and Program
2-1, 1-1. Toward the Presistent Growth of the Organization
2-1, 1-2. Relationship between the Strategy and the Program
2-1, 1-3. Relationship between the Program and the Projects
2-1, 2. Definition and Classification of Programs
2-1, 2-1. Definition of a Program
2-1, 2-2. Classification of Programs
2-1, 2-3. Basic Attributes of a Program
2-1, 3. Program Management
2-1, 3-1. What is Program Management?
2-1, 3-2. Program Integration Management
2-1, 3-2-1. Mission Profiling
2-1, 3-2-2. Program Design
2-1, 3-2-3. Integration Management of Program Implementation
2-1, 3-3. Guidelines for Program Integration Management Activities (1) Zero-Base Idea (2) Flexibility toward Changes (3) Sharing of Knowledge and Information (4) Confirmation of Values
2-1, 4. Lifecycle
2-1, 4-1. Program Lifecycle
2-1, 4-2. Phases and Phase Gates
2-1, 5. Program Organization
2-1, 5-2. Role of the Program Manager
2-2, Program Integration Management
2-2, 1-1. What is Mission Profiling?
2-2, 1-2. Mission Statement
2-2, 1-2-1. Mission Description
2-2, 1-2-2. Value Description
2-2. 1-3. Relationship Analysis of Value
2-2, 1-3-1. Entire Value and Partial Value
2-2, 1-3-2. Stakeholder Value
2-2, 1-4. Scenario Statement
2-2, 1-4-1. Preparation of Scenario Alternatives (1) Implementation Scenario and Environment Scenario (2) Framework for the Preparation of Scenarios
2-2, 1-4-2. Examination of the Feasibility and Selection of Implementation Scenarios (1) Eximination of Feasibility of Scenarios (2) Selection of the Implementation Scenario
2-2, 2-2. Program Architecture
2-2, 2-2-1. What is the Program Architecture?
2-2, 2-2-2. Basic Project Combination Form and Project Model (1) Scheme Model Project (2) System Model Project (3) Service Model Project
2-2, 2-2-3. Process of Architecture Design (1) Establishment of a Program Lifecycle (2) Design of the Project for Putting the Scenario into Practice (3) Program Structuring (4) Allocation of a Role to Each Project (5) Inspection of the Operability and Feasibility of the Program
2-2, 3-1-1. Launching of Program Implementation (1) Overall Assessment of Operations (2) Establishment of the Implementing Body System (3) Launching of Each Project (4) Review of the Implementation Plan
2-2, 3-1-2. Goal Management of Program Implementation (2) Information Communication
2-2, 3-1-3. Program Closing
2-2, 4. (1) Need for Relationship Management in the Program (2) Establishment of Multi-tier Customer Relationships
2-2, 5. Multi-project Management
2-2, 5-1. What is Multi-project?
2-2, 5-2. Key points in Multi-project Management
2-2, 5-2-1. Project management Culture and Business Management Standards
2-2, 5-2-2. Organization Types and Authority Standards
2-2, 5-2-3. Project Management Appraisal System
2-3, 1. Program Strategies and Risks
2-3, 1-1. Strategies in the Program
2-3, 1-3. Strategic Apporoach in Japanese-style Organizations and Japanese-style Program Management
2-3, 2. Program Strategy Management
2-3, 2-1. What is Program Strategy Management?
2-3, 2-2. Strategic Goal Management
2-3, 2-2-1. Effectiveness of Program Goals (1) Effectiveness and Efficiency (2) Timing (3) Uniqueness of Value
2-3, 2-2-3. Expandability of the Program (1) Expandability of the Program Itself (2) Expandability Brought to the Organization by the Program
2-3, 2-3. Implementation Strategy Management
2-3, 2-4. Organizational Strategies and the Program (1) Strategy-type programs (2) Operation-type Program
2-3, 3-1. Program Strategy Management and Risks
2-3, 3-2. Risk Factors and Countermeasures
2-3, 3-4. Development of Risk-sensitive Professionals
2-4, 1. Value Assessment Management
2-4, 1-1. Value and Index (1) Definition of Value and Value Index (2) Value Creation Roadmap
2-4, 1-2. Mechanism for Creating Values
2-4, 1-3. Intangible Assets
2-4, 1-4. Type of Programs and Value Viewpoints
2-4, 1-5. Assets and Resources
2-4, 2. Process of Value Assessment
2-4, 2-1. Purpose of Value Assessment (1) Making Management Decisions (2) Financial Evaluation on the Program Achievements (3) Learning as an Organization
2-4, 2-2. Methods of Value Assessment (1) Recognition of program values (2) Program Value Assessment Process (3) Indices in Projects
2-4, 2-3. Corporate Accounting Techniques (1) Financial Accounting and Managerial Accounting (2) Financial Accounting Information and Business Analysis (3) Managerial Accounting Information
2-4, 2-4. Assessing Present Values
2-4, 2-5. Value of Intangible Assets
2-4, 2-5-1. Increased Significance of Intangible Assets
2-4, 2-5-2. Evaluating the Value of Intangible Assets (1) Quantitative Evaluation (2) Qulitative Evaluation
2-4, 2-6. (1) Designing Program Value Assessments (2) Multiplex Evaluation Method (3) Project & Program Balance Score Card, Pbudgeting
2-4, 2-7. Evaluating the Value of Non-commercial Programs (1) Evaluating the Value of Non-commercial Programs (2) Using the Valuation of Non-commercial Programs
2-4, 3. Value assessment Indices
2-4, 3-1. Example of BSC Targets and Evaluation Indices
2-4, 3-2. Example of Evaluation Indies for the Business Model Gallery
2-4, 3-3. Well-balanced Evaluation Indices
2-4, 3-4. SMART