## Overview Mapping
STANDARDS MAPPING OVERVIEW
ISO 21502:2020(E) | GAPPS Getting stuff done | IPMA ICB4 | PMI PMBOK7
Project, programme and portfolio management — Guidance on project management |  |  |  | NO Mapping
Partial/Some Mapping
4 Project management concepts |  |  |  | Full Mapping
4.1 Overview
4.1.1 General
4.1.2 Projects
4.1.3 Project management
4.2 Context
4.2.1 Impact of a project’s context
4.2.2 Organizational strategy and projects
4.2.3 Customer and supplier perspective
4.2.4 Project constraints
4.2.5 Projects as stand-alone, part of a programme or part of a portfolio
4.3 Project governance
4.3.1 Governance framework
4.3.2 Business case
4.4 Project life cycle
4.5 Project organization and roles
4.5.1 Project organization
4.5.2 Sponsoring organization
4.5.3 Project board
4.5.4 Project sponsor
4.5.5 Project assurance
4.5.6 Project manager
4.5.7 Project office
4.5.8 Work package leader
4.5.9 Project team members
4.5.10 Project stakeholders
4.5.11 Other roles
4.6 Competencies of project personnel
5 Prerequisites for formalizing project management
5.1 Overview
5.2 Considerations for implementing project management
5.3 Continuous improvement of the project management environment
5.4 Alignment with organizational processes and systems
6 Integrated project management practices
6.1 Overview
6.2 Pre-project activities | 0 | 1 | 1
6.3 Overseeing a project | 0 | 1 | 1
6.4 Directing a project | 0 | 1 | 1
6.5 Initiating a project
6.5.1 Overview
6.5.2 Project team mobilization | 0.5 | 1 | 1
6.5.3 Project governance and management approach | 0.5 | 1 | 0.5
6.5.4 Initial project justification | 1 | 1 | 1
6.5.5 Initial project planning | 1 | 1 | 0.5
6.6 Controlling a project
6.6.1 Overview
6.6.2 Progressive justification . | 1 | 1 | 0.5
6.6.3 Managing project performance | 0.5 | 1 | 1
6.6.4 Managing the start and close of each project phase | 0.5 | 1 | 1
6.6.5 Managing the start, progress and close of each work package | 0.5 | 1 | 0.5
6.7 Managing delivery | 0.5 | 1 | 1
6.8 Closing or terminating a project | 0 | 1 | 0.5
6.9 Post-project activities | 0 | 0.5 | 0
7 Management practices for a project
7.1 Overview
7.2 Planning
7.2.1 Overview
7.2.2 Developing the plan | 1 | 1 | 1
7.2.3 Monitoring the plan | 1 | 1 | 1
7.3 Benefit management
7.3.1 Overview
7.3.2 Identifying and analysing benefits | 1 | 1 | 0.5
7.3.3 Monitoring benefits | 1 | 1 | 0.5
7.3.4 Maintaining benefits | 1 | 1 | 0.5
7.4 Scope management
7.4.1 Overview
7.4.2 Defining the scope | 1 | 1 | 1
7.4.3 Controlling the scope | 1 | 1 | 0.5
7.4.4 Confirming scope delivery | 1 | 1 | 0.5
7.5 Resources management
7.5.1 Overview
7.5.2 Planning the project organization | 0.5 | 1 | 0
7.5.3 Establishing the team | 0.5 | 1 | 1
7.5.4 Developing the team | 1 | 1 | 1
7.5.5 Managing the team | 1 | 1 | 1
7.5.6 Planning, managing and controlling physical and material resources | 0 | 1 | 1
7.6 Schedule management
7.6.1 Overview
7.6.2 Estimating activity durations | 0.5 | 1 | 1
7.6.3 Developing the schedule | 0.5 | 1 | 1
7.6.4 Controlling the schedule | 0.5 | 1 | 1
7.7 Cost management
7.7.1 Overview
7.7.2 Estimating cost | 0 | 1 | 1
7.7.3 Developing the budget | 0 | 1 | 1
7.7.4 Controlling costs | 0 | 1 | 1
7.8 Risk management
7.8.1 Overview
7.8.2 Identifying risk | 0.5 | 1 | 1
7.8.3 Assessing risk | 0.5 | 1 | 1
7.8.4 Treating risk | 0.5 | 1 | 1
7.8.5 Controlling risk | 0.5 | 1 | 1
7.9 Issues management
7.9.1 Overview
7.9.2 Identifying issues | 0.5 | 1 | 1
7.9.3 Resolving issues | 1 | 1 | 1
7.10 Change control
7.10.1 Overview
7.10.2 Establishing a change control framework | 0.5 | 1 | 1
7.10.3 Identifying and assessing change requests | 0.5 | 1 | 1
7.10.4 Planning the implementation of change requests | 0.5 | 1 | 1
7.10.5 Implementing and closing change requests | 0.5 | 1 | 1
7.11 Quality management
7.11.1 Overview
7.11.2 Planning quality | 0.5 | 1 | 0.5
7.11.3 Assuring quality | 0.5 | 1 | 0.5
7.11.4 Controlling quality | 0.5 | 1 | 0.5
7.12 Stakeholder engagement
7.12.1 Overview
7.12.2 Identifying stakeholders | 0.5 | 1 | 1
7.12.3 Engaging stakeholders | 1 | 1 | 1
7.13 Communication management
7.13.1 Overview
7.13.2 Planning communication | 1 | 1 | 1
7.13.3 Distributing information | 0.5 | 1 | 1
7.13.4 Monitoring the impact of communication | 0.5 | 1 | 1
7.14 Managing organizational and societal change
7.14.1 Overview
7.14.2 Identifying the need for change | 0 | 1 | 0.5
7.14.3 Implementing the organizational and societal change | 0 | 1 | 1
7.15 Reporting
7.15.1 Overview
7.15.2 Planning reporting | 0 | 1 | 1
7.15.3 Managing reporting | 0 | 1 | 1
7.15.4 Delivering reports | 0 | 1 | 1
7.16 Information and documentation management
7.16.1 Overview
7.16.2 Identifying which information should be managed | 0.5 | 1 | 1
7.16.3 Storing and retrieving information and documentation | 0.5 | 1 | 1
7.17 Procurement
7.17.1 Overview
7.17.2 Planning procurement | 0 | 1 | 0.5
7.17.3 Evaluating and selecting suppliers | 0 | 1 | 0
7.17.4 Administering contracts | 0 | 1 | 0.5
7.17.5 Closing contracts | 0 | 1 | 0
7.18 Lessons learned
7.18.1 Overview
7.18.2 Identifying lessons | 1 | 1 | 1
7.18.3 Disseminating lessons | 1 | 1 | 0.5
| 32 | 63.5 | 51.5
Percentage coverage | 50% | 99.22% | 80.47%

## GAPPS
Mapping: GAPPS Getting Stuff Done Framework to ISO 21502 Standard
The intent of the GAPPS mapping process is to use the ISO 21502 standard as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. Therefore, this is a mapping of the COVERAGE only of the GAPPS Getting Stuff Done Framework at the Element and KCI level against the ISO 21502 Standard. The process used for mapping of standards against the ISO 21502 standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS TLF 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS TLF 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the ISO 21502 standard has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. Topics or activities that are included in other standards, but not included in the ISO 21502 standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the ISO 21502 standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case GAPPS Getting Stuff Done Framework) maps against the ISO 21502 standard. This mapping has been reviewed by GAPPS
LEGEND:
No mapping completed
Partial or some mapping completed
Full mapping completed
ISO 21502:2020(E)
Project, programme and portfolio management — Guidance on project management
4 Project management concepts
4.1 Overview
4.1.1 General
4.1.2 Projects
4.1.3 Project management
4.2 Context
4.2.1 Impact of a project’s context
4.2.2 Organizational strategy and projects
4.2.3 Customer and supplier perspective
4.2.4 Project constraints
4.2.5 Projects as stand-alone, part of a programme or part of a portfolio
4.3 Project governance
4.3.1 Governance framework
4.3.2 Business case
4.4 Project life cycle
4.5 Project organization and roles
4.5.1 Project organization
4.5.2 Sponsoring organization
4.5.3 Project board
4.5.4 Project sponsor
4.5.5 Project assurance
4.5.6 Project manager
4.5.7 Project office
4.5.8 Work package leader
4.5.9 Project team members
4.5.10 Project stakeholders
4.5.11 Other roles
4.6 Competencies of project personnel
5 Prerequisites for formalizing project management
5.1 Overview
5.2 Considerations for implementing project management
5.3 Continuous improvement of the project management environment
5.4 Alignment with organizational processes and systems
6 Integrated project management practices
6.1 Overview
6.2 Pre-project activities
6.3 Overseeing a project
6.4 Directing a project
6.5 Initiating a project
6.5.1 Overview
6.5.2 Project team mobilization | G Maintain commitment, momentum and direction
6.5.3 Project governance and management approach | F Build relationships based on trust F Appreciate and respect others F Stimulate an open and creative environment M Work within structures of decision making W Make informed choices that balance people, planet and profit and control
6.5.4 Initial project justification | A Iteratively define purpose and agree value to be delivered F Establish a compelling proposition D Use imagination W Ensure what you are doing is of value L Draw on the experience of others W Consider impact on the environment and future generations
6.5.5 Initial project planning | D Explore diverse views D Use imagination L Draw on the experience of others G Plan, sequence and dynamically adjust the work
6.6 Controlling a project
6.6.1 Overview
6.6.2 Progressive justification . | A Periodically re-visit the agreement and the why M Enable direction, decisions and alignment with purpose
6.6.3 Managing project performance | G Maintain commitment, momentum and direction
6.6.4 Managing the start and close of each project phase | W Prepare users to accept the work that you have completed G Plan, sequence and dynamically adjust the work
6.6.5 Managing the start, progress and close of each work package | W Prepare users to accept the work that you have completed
6.7 Managing delivery | W Prepare users to accept the work that you have completed
6.8 Closing or terminating a project | W Prepare users to accept the work that you have completed
6.9 Post-project activities | L Manage knowledge
7 Management practices for a project
7.1 Overview
7.2 Planning
7.2.1 Overview
7.2.2 Developing the plan | A Plan action to achieve objectives G Plan, sequence and dynamically adjust the work D Explore diverse views L Draw on the experience of others
7.2.3 Monitoring the plan | G Plan, sequence and dynamically adjust the work
7.3 Benefit management
7.3.1 Overview
7.3.2 Identifying and analysing benefits | D Explore diverse views D Use imagination W Ensure what you are doing is of value L Draw on the experience of others A Iteratively define purpose and agree value to be delivered W Consider impact on the environment and future generations
7.3.3 Monitoring benefits | W Ensure what you are doing is of value L Draw on the experience of others W Consider impact on the environment and future generations
7.3.4 Maintaining benefits | A Periodically re-visit the agreement and the why D Consider consequences W Ensure what you are doing is of value W Consider impact on the environment and future generations
7.4 Scope management
7.4.1 Overview
7.4.2 Defining the scope | A Document requirements A Plan action to achieve objectives
7.4.3 Controlling the scope | A Periodically re-visit the agreement and the why G Plan, sequence and dynamically adjust the work A Iteratively define purpose and agree value to be delivered
7.4.4 Confirming scope delivery | W Prepare users to accept the work that you have completed
7.5 Resources management
7.5.1 Overview
7.5.2 Planning the project organization | F Establish a compelling proposition
7.5.3 Establishing the team | D Set expectations
7.5.4 Developing the team | F Cultivate team performance D Explore diverse views D Be resilient
7.5.5 Managing the team | G Use facilitation to achieve goals G Facilitate creativity G Maintain commitment, momentum and direction F Appreciate and respect others F Stimulate an open and creative environment D Be resilient M Prioritise and manage personal time W Look after yourself and others G Honour agreements
7.5.6 Planning, managing and controlling physical and material resources | M Prioritise and manage personal time
7.6 Schedule management
7.6.1 Overview
7.6.2 Estimating activity durations | G Plan, sequence and dynamically adjust the work
7.6.3 Developing the schedule | G Plan, sequence and dynamically adjust the work
7.6.4 Controlling the schedule | G Plan, sequence and dynamically adjust the work
7.7 Cost management
7.7.1 Overview
7.7.2 Estimating cost
7.7.3 Developing the budget
7.7.4 Controlling costs
7.8 Risk management
7.8.1 Overview
7.8.2 Identifying risk | D Consider consequences D Use imagination
7.8.3 Assessing risk | D Consider consequences D Use imagination
7.8.4 Treating risk | G Take action D Consider consequences D Use imagination M Make timely decisions in face of uncertainty
7.8.5 Controlling risk | M Make timely decisions in face of uncertainty
7.9 Issues management
7.9.1 Overview
7.9.2 Identifying issues | M Apply ethical reasoning with integrity
7.9.3 Resolving issues | G Take action D Be proactive and forward thinking M Enable direction, decisions and alignment with purpose M Be courageous in making risky or unpopular decisions M Make timely decisions in face of uncertainty M Take initiative
7.10 Change control
7.10.1 Overview
7.10.2 Establishing a change control framework | G Embrace change
7.10.3 Identifying and assessing change requests | G Embrace change
7.10.4 Planning the implementation of change requests | G Embrace change
7.10.5 Implementing and closing change requests | G Embrace change
7.11 Quality management
7.11.1 Overview
7.11.2 Planning quality | W Ensure what you are doing is of value W Make informed choices that balance people, planet and profit W Consider impact on the environment and future generations
7.11.3 Assuring quality | W Ensure what you are doing is of value W Make informed choices that balance people, planet and profit W Consider impact on the environment and future generations
7.11.4 Controlling quality | W Prepare users to accept the work that you have completed
7.12 Stakeholder engagement
7.12.1 Overview
7.12.2 Identifying stakeholders | D Explore diverse views
7.12.3 Engaging stakeholders | G Take action G Manage expectations A Ensure aligned vision between relevant parties F Build relationships based on trust F Proactively communicate with stakeholders D Explore diverse views D Set expectations W Prepare users to accept the work that you have completed W Look after yourself and others G Honour agreements
7.13 Communication management
7.13.1 Overview
7.13.2 Planning communication | F Proactively communicate with stakeholders
7.13.3 Distributing information | F Proactively communicate with stakeholders
7.13.4 Monitoring the impact of communication | D Consider consequences
7.14 Managing organizational and societal change
7.14.1 Overview
7.14.2 Identifying the need for change | G Embrace change
7.14.3 Implementing the organizational and societal change | G Embrace change
7.15 Reporting
7.15.1 Overview
7.15.2 Planning reporting
7.15.3 Managing reporting
7.15.4 Delivering reports
7.16 Information and documentation management
7.16.1 Overview
7.16.2 Identifying which information should be managed | L Manage knowledge
7.16.3 Storing and retrieving information and documentation | L Manage knowledge
7.17 Procurement
7.17.1 Overview
7.17.2 Planning procurement
7.17.3 Evaluating and selecting suppliers
7.17.4 Administering contracts
7.17.5 Closing contracts
7.18 Lessons learned
7.18.1 Overview
7.18.2 Identifying lessons | L Build on what you already have, L Learn continually L Manage knowledge L Reflect on practice, experience, and results L Draw on the experience of others
7.18.3 Disseminating lessons | L Capture and share stories and insights L Manage knowledge
Overs:
F Employ humour and sense of perspective

## ICB4
Mapping: ICB® Version 4.0 to ISO 21502 Standard
The intent of the GAPPS mapping process is to use the ISO 21502 standard as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. Therefore, this is a mapping of the COVERAGE only of the ICB® 4.0 at the Element and KCI level against the ISO 21502 Standard. The ICB® 4.0 includes Technical (practise), Contextual (perspective) and Behavioural (people) competencies. All of these have been mapped against the ISO 21502 standard. The process used for mapping of standards against the ISO 21502 standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS TLF 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS TLF 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the ISO 21502 standard has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. Topics or activities that are included in other standards, but not included in the ISO 21502 standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the ISO 21502 standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case the ICB® 4.0) maps against the ISO 21502 standard. This mapping has been reviewed by IPMA
LEGEND:
No mapping completed
Partial or some mapping completed
Full mapping completed
ISO 21502:2020(E)
Project, programme and portfolio management — Guidance on project management
4 Project management concepts
4.1 Overview
4.1.1 General
4.1.2 Projects
4.1.3 Project management
4.2 Context
4.2.1 Impact of a project’s context
4.2.2 Organizational strategy and projects
4.2.3 Customer and supplier perspective
4.2.4 Project constraints
4.2.5 Projects as stand-alone, part of a programme or part of a portfolio
4.3 Project governance
4.3.1 Governance framework
4.3.2 Business case
4.4 Project life cycle
4.5 Project organization and roles
4.5.1 Project organization
4.5.2 Sponsoring organization
4.5.3 Project board
4.5.4 Project sponsor
4.5.5 Project assurance
4.5.6 Project manager
4.5.7 Project office
4.5.8 Work package leader
4.5.9 Project team members
4.5.10 Project stakeholders
4.5.11 Other roles
4.6 Competencies of project personnel
5 Prerequisites for formalizing project management
5.1 Overview
5.2 Considerations for implementing project management
5.3 Continuous improvement of the project management environment
5.4 Alignment with organizational processes and systems
6 Integrated project management practices
6.1 Overview
6.2 Pre-project activities | 4.3.1.1 Align with organisational mission and vision 4.3.1.2 Identify and exploit opportunities to influence organisational strategy
6.3 Overseeing a project | 4.3.1.4 Determine, assess and review critical success factors 4.3.1.5 Determine, assess and review key performance indicators
6.4 Directing a project | 4.3.1.4 Determine, assess and review critical success factors 4.3.1.5 Determine, assess and review key performance indicators
6.5 Initiating a project
6.5.1 Overview
6.5.2 Project team mobilization | 4.3.2.6 Align the project with human resource processes and functions
6.5.3 Project governance and management approach | 4.3.2.1 Know the principles of project management and the way they are implemented 4.3.2.5 Align the project with the organisation’s decision-making and reporting structures 48 and quality requirements
6.5.4 Initial project justification | 4.3.2.7 Align the project with finance and control 49 processes and functions
6.5.5 Initial project planning | 4.3.2.4 Supporting functions 4.3.2.7 Align the project with finance and control 49 processes and functions
6.6 Controlling a project
6.6.1 Overview
6.6.2 Progressive justification . | 4.3.1.3 Develop and ensure the ongoing validity of the business / organisational justification 4.5.10.2 Initiate and manage the transition to a new project phase 4.5.10.5 Assess, get agreement on, and implement project changes
6.6.3 Managing project performance | 4.1. Managing projects 4.3.2.1 Know the principles of project management and the way they are implemented 4.3.2.5 Align the project with the organisation’s decision-making and reporting structures 48 and quality requirements 4.3.2.6 Align the project with human resource processes and functions 4.3.2.7 Align the project with finance and control 49 processes and functions 4.5.4.5 Monitor progress against the schedule and make any necessary adjustments
6.6.4 Managing the start and close of each project phase | 4.5.4.3 Decide on schedule and stage approach 4.5.6.3 Verify the achievement of project quality objectives and recommend any necessary corrective and/or preventive actions 4.5.10.2 Initiate and manage the transition to a new project phase 4.5.10.6 Close and evaluate a phase or the project
6.6.5 Managing the start, progress and close of each work package | 4.5.10.3 Control project performance against the project plan and take any necessary remedial actions 4.5.5.3 Establish infrastructure, processes and systems for information flow 4.5.5.4 Implement, monitor and maintain the organisation of the project 4.5.4.5 Monitor progress against the schedule and make any necessary adjustments 4.5.3.3 Define the work packages of the project
6.7 Managing delivery | 4.5.2.1 Define and develop the project goal hierarchy 4.5.2.3 Prioritise and decide on requirements and acceptance criteria 4.5.3.1 Define the project deliverables 4.4.10.5 Deliver results and get acceptance
6.8 Closing or terminating a project | 4.5.10.6 Close and evaluate a phase or the project
6.9 Post-project activities | 4.5.10.6 Close and evaluate a phase or the project
7 Management practices for a project
7.1 Overview
7.2 Planning
7.2.1 Overview
7.2.2 Developing the plan | 4.5.10.1 Start the project and develop and get agreement on the project management plan 4.5.1.5 Design the project execution architecture
7.2.3 Monitoring the plan | 4.5.10.3 Control project performance against the project plan and take any necessary remedial actions
7.3 Benefit management
7.3.1 Overview
7.3.2 Identifying and analysing benefits | 4.3.1.1 Align with organisational mission and vision 4.3.1.4 Determine, assess and review critical success factors 4.3.1.5 Determine, assess and review key performance indicators 4.5.5.1 Assess and determine the needs of stakeholders relating to information and documentation
7.3.3 Monitoring benefits | 4.3.1.3 Develop and ensure the ongoing validity of the business / organisational justification 4.3.1.4 Determine, assess and review critical success factors 4.3.1.5 Determine, assess and review key performance indicators 4.5.5.1 Assess and determine the needs of stakeholders relating to information and documentation
7.3.4 Maintaining benefits | 4.3.1.3 Develop and ensure the ongoing validity of the business / organisational justification 4.3.1.4 Determine, assess and review critical success factors 4.3.1.5 Determine, assess and review key performance indicators 4.5.5.1 Assess and determine the needs of stakeholders relating to information and documentation 4.4.10.1 Evaluate all decisions and actions against their impact on project success and the objectives of the organisation
7.4 Scope management
7.4.1 Overview
7.4.2 Defining the scope | 4.5.3.1 Define the project deliverables 4.5.3.2 Structure the project scope 4.5.3.3 Define the work packages of the project
7.4.3 Controlling the scope | 4.5.3.4 Establish and maintain scope configuration 4.5.10.3 Control project performance against the project plan and take any necessary remedial actions
7.4.4 Confirming scope delivery | 4.5.10.5 Assess, get agreement on, and implement project changes 4.5.10.6 Close and evaluate a phase or the project
7.5 Resources management
7.5.1 Overview
7.5.2 Planning the project organization | 4.5.8.1 Develop strategic resource plan to deliver the project 4.5.8.2 Define the quality and quantity of resources required 4.5.8.3 Identify the potential sources of resources and negotiate their acquisition 4.5.8.4 Allocate and distribute resources according to defined need
7.5.3 Establishing the team | 4.4.6.1 Select and build the team 4.5.5.2 Define the structure, roles and responsibilities within the project
7.5.4 Developing the team | 4.4.6.2 Promote cooperation and networking between team members 4.4.6.3 Support, facilitate and review the development of the team and its members 4.4.6.4 Empower teams by delegating tasks and responsibilities
7.5.5 Managing the team | 4.4.6.4 Empower teams by delegating tasks and responsibilities 4.4.6.5 Recognise errors to facilitate learning from mistakes 4.4.5.1 Initiate actions and proactively offer help and advice 4.4.5.2 Take ownership and show commitment 4.4.5.3 Provide direction, coaching and mentoring to guide and improve the work of individuals and teams 4.4.5.4 Exert appropriate power and influence over others to achieve the goals
7.5.6 Planning, managing and controlling physical and material resources | 4.5.8.1 Develop strategic resource plan to deliver the project 4.5.8.2 Define the quality and quantity of resources required 4.5.8.3 Identify the potential sources of resources and negotiate their acquisition 4.5.8.4 Allocate and distribute resources according to defined need 4.5.8.5 Evaluate resource usage and take any necessary corrective actions
7.6 Schedule management
7.6.1 Overview
7.6.2 Estimating activity durations | 4.5.4.1 Define / Establish the activities required to deliver the project 4.5.4.2 Determine the work effort and duration of activities
7.6.3 Developing the schedule | 4.5.4.3 Decide on schedule and stage approach 4.5.4.4 Sequence project activities and create a schedule
7.6.4 Controlling the schedule | 4.5.4.5 Monitor progress against the schedule and make any necessary adjustments
7.7 Cost management
7.7.1 Overview
7.7.2 Estimating cost | 4.5.7.1 Estimate project costs
7.7.3 Developing the budget | 4.5.7.2 Establish the project budget
7.7.4 Controlling costs | 4.5.7.4 Develop, establish and maintain a financial management and reporting system for the project 4.5.7.5 Monitor project financials in order to identify and correct deviations from the project plan
7.8 Risk management
7.8.1 Overview
7.8.2 Identifying risk | 4.5.11.1 Develop and implement a risk management framework 4.5.11.2 Identify risks and opportunities
7.8.3 Assessing risk | 4.5.11.3 Assess the probability and impact of risks and opportunities
7.8.4 Treating risk | 4.5.11.4 Select strategies and implement response plan to address risks and opportunities
7.8.5 Controlling risk | 4.5.11.5 Evaluate and monitor risks, opportunities and implemented responses
7.9 Issues management
7.9.1 Overview
7.9.2 Identifying issues | 4.4.7.1 Anticipate and possibly prevent conflicts and crises
7.9.3 Resolving issues | 4.4.7.2 Analyse the causes and consequences of conflicts and crises and select appropriate response(s) 4.4.7.3 Mediate and resolve conflicts and crises and/or their impact
7.10 Change control
7.10.1 Overview
7.10.2 Establishing a change control framework | 4.5.13.3 Develop change or transformation strategy 4.5.13.4 Implement change or transformation management strategy
7.10.3 Identifying and assessing change requests | 4.5.13.2 Identify change requirements and transformation opportunities 4.5.10.5 Assess, get agreement on, and implement project changes
7.10.4 Planning the implementation of change requests | 4.5.10.5 Assess, get agreement on, and implement project changes
7.10.5 Implementing and closing change requests | 4.5.10.5 Assess, get agreement on, and implement project changes
7.11 Quality management
7.11.1 Overview
7.11.2 Planning quality | 4.5.6.1 Develop, monitor the implementation of, and revise a quality management plan for the project 4.5.6.4 Plan and organise the validation of project outcomes
7.11.3 Assuring quality | 4.5.6.2 Review the project and its deliverables to ensure that they continue to meet the requirements of the quality management plan 4.5.6.3 Verify the achievement of project quality objectives and recommend any necessary corrective and/or preventive actions 4.5.6.5 Ensure quality throughout the project
7.11.4 Controlling quality | 4.5.6.2 Review the project and its deliverables to ensure that they continue to meet the requirements of the quality management plan 4.5.6.3 Verify the achievement of project quality objectives and recommend any necessary corrective and/or preventive actions 4.5.6.5 Ensure quality throughout the project
7.12 Stakeholder engagement
7.12.1 Overview
7.12.2 Identifying stakeholders | 4.5.12.1 Identify stakeholders and analyse their interests and influence 4.3.4.1 Assess the personal ambitions and interests of others and the potential impact of these on the project 4.3.4.2 Assess the informal influence of individuals and groups and its potential impact on the project
7.12.3 Engaging stakeholders | 4.5.12.2 Develop and maintain a stakeholder strategy and communication plan 4.5.12.3 Engage with the executive, sponsors and higher management to gain commitment and to manage interests and expectations 4.5.12.4 Engage with users, partners, suppliers and other stakeholders to gain their cooperation and commitment 4.5.12.5 Organise and maintain networks and alliances 4.5.2.2 Identify and analyse the project stakeholder needs and requirements
7.13 Communication management
7.13.1 Overview
7.13.2 Planning communication | 4.4.3.3 Choose communication styles and channels to meet the needs of the audience, situation and management level 4.5.5.1 Assess and determine the needs of stakeholders relating to information and documentation 4.5.5.3 Establish infrastructure, processes and systems for information flow
7.13.3 Distributing information | 4.4.3.1 Provide clear and structured information 70 to others and verify their understandin 4.4.2.4 Act, take decisions and communicate in a consistent way
7.13.4 Monitoring the impact of communication | 4.4.3.1 Provide clear and structured information 70 to others and verify their understandin
7.14 Managing organizational and societal change
7.14.1 Overview
7.14.2 Identifying the need for change | 4.5.13.1 Assess the adaptability to change of the organisation(s) 4.5.13.2 Identify change requirements and transformation opportunities 4.5.13.3 Develop change or transformation strategy
7.14.3 Implementing the organizational and societal change | 4.5.5.4 Implement, monitor and maintain the organisation of the project 4.5.13.4 Implement change or transformation management strategy
7.15 Reporting
7.15.1 Overview
7.15.2 Planning reporting | 4.3.2 Governance, structures and processes
7.15.3 Managing reporting | 4.3.2.4 Supporting functions 4.3.2.5 Align the project with the organisation’s decision-making and reporting structures 48 and quality requirements 4.4.6.4 Empower teams by delegating tasks and responsibilities
7.15.4 Delivering reports | 4.4.6.4 Empower teams by delegating tasks and responsibilities 4.5.10.3 Control project performance against the project plan and take any necessary remedial actions 4.5.10.4 Report on project progres
7.16 Information and documentation management
7.16.1 Overview
7.16.2 Identifying which information should be managed | 4.5.5.1 Assess and determine the needs of stakeholders relating to information and documentation 4.5.1.4 Select and review the overall project management approach
7.16.3 Storing and retrieving information and documentation | 4.5.5.3 Establish infrastructure, processes and systems for information flow 4.3.2.4 Supporting functions
7.17 Procurement
7.17.1 Overview
7.17.2 Planning procurement | 4.5.9.1 Agree on procurement needs, options and processes
7.17.3 Evaluating and selecting suppliers | 4.5.9.2 Contribute to the evaluation and selection of suppliers and partners
7.17.4 Administering contracts | 4.5.9.3 Contribute to the negotiation and agreement of contractual terms and conditions that meet project objectives
7.17.5 Closing contracts | 4.5.9.4 Supervise the execution of contracts, address issues and seek redress where necessary
7.18 Lessons learned
7.18.1 Overview
7.18.2 Identifying lessons | 4.5.1.2 Review, apply and exchange lessons learned from and with other projects 4.4.7.4 Identify and share learning from conflicts and crises in order to improve future practice
7.18.3 Disseminating lessons | 4.5.1.2 Review, apply and exchange lessons learned from and with other projects 4.4.7.4 Identify and share learning from conflicts and crises in order to improve future practice
Overs
4.3.2.2 Know and apply the principles of programme management and the way they are implemented
4.3.2.3 Secure project funding
4.3.3.1 Identify and ensure that the project complies with all relevant legislation
4.3.3.2 Identify and ensure that the project complies with all relevant health, safety, security and environmental regulations (HSSE)
4.3.3.3 Identify and ensure that the project complies with all relevant codes of conduct and professional regulation
4.3.3.4 Identify and ensure that the project complies with relevant sustainability principles and objectives
4.3.3.5 Assess, use and develop professional standards and tools for the project
4.3.3.6 Assess, benchmark and improve the organisational project management competence
4.3.4.3 Assess the personalities and working styles of others and employ them to the benefit of the project
4.3.5.1 Assess the culture and values of the society and their implications for the project
4.3.5.2 Align the project with the formal culture and corporate values of the organisation
4.3.5.3 Assess the informal culture and values of the organisation and their implications for the project
4.4.1.1 Identify, and reflect on the ways in which own values and experiences affect the work
4.4.1.2 Build self-confidence on the basis of personal strengths and weaknesses
4.4.1.3 Identify, and reflect on, personal motivations to set personal goals and keep focus
4.4.1.4 Organise personal work depending on the situation and own resources
4.4.1.5 Take responsibility for personal learning and development
4.4.2.1 Acknowledge and apply ethical values to all decisions and actions
4.4.2.2 Promote the sustainability of outputs and outcomes
4.4.2.3 Take responsibility for own decisions and actions
4.4.2.5 Complete tasks thoroughly in order to build confidence with others
4.4.3.2 Facilitate and promote open communication
4.4.3.4 Communicate effectively with virtual teams
4.4.3.5 Employ humour and sense of perspective 71 when appropriate
4.4.4.1 Initiate and develop personal and professional relationships
4.4.4.2 Build, facilitate and contribute to social networks
4.4.4.3 Demonstrate empathy through listening, understanding and support
4.4.4.4 Show confidence and respect by encouraging others to share their opinions or concerns
4.4.4.5 Share own vision and goals in order to gain the engagement and commitment of others
4.4.5.5 Make, enforce and review decisions
4.4.8.1 Stimulate and support an open and creative environment
4.4.8.2 Apply conceptual thinking to define situations and strategies
4.4.8.3 Apply analytic techniques to analysing situations, financial and organisational data and trends
4.4.8.4 Promote and apply creative techniques to 90 find alternatives and solutions
4.4.8.5 Promote a holistic view of the project and its context to improve decision-making
4.4.9.1 Identify and analyse the interests of all parties involved in the negotiation
4.4.9.2 Develop and evaluate options and alternatives with the potential to meet the needs of all parties
4.4.9.3 Define a negotiation strategy in line with own objectives that is acceptable to all parties involved
4.4.9.4 Reach negotiated agreements with other parties that are in line with own objectives
4.4.9.5 Detect and exploit additional selling and acquisition possibilities
4.4.10.2 Balance needs and means to optimise outcomes and success
4.4.10.3 Create and maintain a healthy, safe and productive working environment
4.4.10.4 Promote and ‘sell’ the project, its processes and outcomes
4.5.1.1 Acknowledge, prioritise and review success criteria
4.5.1.3 Determine complexity and its consequences for the approach
4.5.7.3 Secure project funding

## PMBOK7
Mapping: PMBOK® Guide SeventhEd to ISO 21502 Standard
The intent of the GAPPS mapping process is to use the ISO 21502 standard as a common basis or spine for mapping of the COVERAGE of other project management standards for the purpose of comparison. Therefore, this is a mapping of the COVERAGE only of the PMBOK® Guide at the Element level against the ISO 21502 Standard. The process used for mapping of standards against the ISO 21502 standard is as follows: 1. Initial mapping by a subject matter expert or informed independent party 2. Review of the mapping by a working party at a GAPPS TLF 3. Draft mapping send to the owner of the mapped standard for review and feedback – specifying a time period for response 4. If no response is received from the mapped standard's owner within the specified time period, proceed to (6) 5. Review and respond to feedback from mapped standard's owner, and make any proposed changes to the mapping subject to agreement by a working party at a GAPPS TLF 6. Submit mapping to GAPPS Board for approval 7. Publish on the GAPPS website – noting whether or not the mapping has been reviewed and approved by the standards owner.
As each set of standards that can be mapped to the ISO 21502 standard has its own purpose, focus and format a direct (one-to-one) mapping is not expected or sought. The aim is merely to provide a basis for the comparison of coverage. Topics or activities that are included in other standards, but not included in the ISO 21502 standard, are listed at the bottom of the document. These additional topics are what differentiates the mapped standards from the ISO 21502 standard. The right hand column below is coloured according to the following Legend to indicate the extent to which the coverage of the standard (in this case PMBOK® Guide SeventhEd) maps against the ISO 21502 standard. This mapping has been reviewed by PMI
LEGEND:
No mapping completed
Partial or some mapping completed
Full mapping completed
ISO 21502:2020(E) | A GUIDE TO THE PROJECT MANAGEMENT BODY OF KNOWLEDGE (PMBOK® Guide) SeventhEd_ENG
Project, programme and portfolio management — Guidance on project management | Comment from PMI: "Project Management is covered in the 2 part binding which contains The Standard for Project Management and the PMBOK ® Guide. Some of the topics that are not in the PMBOK® are captured in the standard."
4 Project management concepts
4.1 Overview
4.1.1 General
4.1.2 Projects
4.1.3 Project management
4.2 Context
4.2.1 Impact of a project’s context
4.2.2 Organizational strategy and projects
4.2.3 Customer and supplier perspective
4.2.4 Project constraints
4.2.5 Projects as stand-alone, part of a programme or part of a portfolio
4.3 Project governance
4.3.1 Governance framework
4.3.2 Business case
4.4 Project life cycle
4.5 Project organization and roles
4.5.1 Project organization
4.5.2 Sponsoring organization
4.5.3 Project board
4.5.4 Project sponsor
4.5.5 Project assurance
4.5.6 Project manager
4.5.7 Project office
4.5.8 Work package leader
4.5.9 Project team members
4.5.10 Project stakeholders
4.5.11 Other roles
4.6 Competencies of project personnel
5 Prerequisites for formalizing project management
5.1 Overview
5.2 Considerations for implementing project management
5.3 Continuous improvement of the project management environment
5.4 Alignment with organizational processes and systems
6 Integrated project management practices
6.1 Overview
6.2 Pre-project activities | 3.4.1 Select initial development approach 3.4.2 Tailor for the organization 3.4.3 Tailor for the project 2.1.1 Stakeholder engagement
6.3 Overseeing a project | 2.5.3 Maintaining project team focus 2.5.7 Monitoring new work and changes 4.6.7 Reports 2.4.7 Changes 2.4.11 Checking results 2.5.5 Managing physical resources 2.7.3 Presenting information 4.4.3 Meetings and events 4.6.2 Logs and registers 4.6.3 Plans 4.6.5 Baselines
6.4 Directing a project | 2.7.2 What to measure 4.4.1 Data gathering and analysis 2.3.6 Aligning of delivery cadence, development approach, and life cycle 2.3.7 Interactions with other performance domains 2.6.1 Delivery of value 2.7.8 Checking results
6.5 Initiating a project
6.5.1 Overview
6.5.2 Project team mobilization | 2.2.1 Project team management and leadership 2.1.1.1 Identify 2.2.2 Project team culture 2.2.3 High-performing project teams 2.2.4 Leadership skills 2.2.5 Tailoring leadership styles
6.5.3 Project governance and management approach | 2.2.5 Tailoring leadership styles 2.4.2 Planning variables 2.5.1 Project processes 2.6.2 Deliverables 3.3.1 Life cycle and development approach selection 3.4.2 Tailor for the organization 3.4.1 Select initial development approach 3.5.3 Development approach and life cycle 3.7 Summary
6.5.4 Initial project justification | 2.6.1 Delivery of value 4.4.1 Data gathering and analysis
6.5.5 Initial project planning | 2.2.2.1 Identify 2.2.1.3 Common Aspects of Team Development 2.3.1 Development, cadence, and life cycle relationship 2.4.1 Planning overview 2.1.1 Stakeholder engagement 3.3.1 Development approach and life cycle 3.4.3 Tailor for the project
6.6 Controlling a project
6.6.1 Overview
6.6.2 Progressive justification . | 2.5.7 Monitoring new work and changes
6.6.3 Managing project performance | 2.7.1 Establishing effective measures 2.7.2 What to measure 2.7.3 Presenting information 2.7.4 Measurement pitfalls 2.7.5 Troubleshooting performance 2.7.6 Growing and improving 2.7.7 Interactions with other performance domains 2.7.8 Checking results
6.6.4 Managing the start and close of each project phase | 2.3.5 Life cycle and phase definitions 2.3.8 Measuring outcomes 2.4.2.2 Estimating
6.6.5 Managing the start, progress and close of each work package | 2.6.2.2 Scope Definition
6.7 Managing delivery | 2.6.2 Deliverables 2.3.2 Delivery cadence 2.5.5 Managing physical resources 3.5.6 Delivery 3.4.3.1 Product/Deliverable
6.8 Closing or terminating a project | 2.3.5 Life cycle and phase definitions 2.3.6 Aligning of delivery cadence, development approach, and life cycle 2.7 Measurement performance domain 4.2.7.4 Process Group
6.9 Post-project activities
7 Management practices for a project
7.1 Overview
7.2 Planning
7.2.1 Overview
7.2.2 Developing the plan | 2.4 Planning performance domain
7.2.3 Monitoring the plan | 2.5.Project work performance domain
7.3 Benefit management
7.3.1 Overview
7.3.2 Identifying and analysing benefits | 4.4.1 Data gathering and analysis 4.6.1 Strategy artifacts 3.5.8 Measurements
7.3.3 Monitoring benefits | 3.5.8 Measurements 2.7.2.5 Business Value 4.2.7.4 Process Groups 2.6.6 Checking results
7.3.4 Maintaining benefits | 3.5.8 Measurements 2.7.2.5 Business Value 4.2.7.5 Salience Model 3.5.8 Measurements
7.4 Scope management
7.4.1 Overview
7.4.2 Defining the scope | 2.6.2.2 Scope Definition 2.6.2 Deliverables 2.4.2.1 Delivery 4.6.3 Plans 4.6.4 Hierarchy charts 4.6.5 Baselines
7.4.3 Controlling the scope | 2.5.10 Checking results 2.5.7 Monitoring new work and changes 2.4.11 Checking results 2.6.6 Checking results
7.4.4 Confirming scope delivery | 2.3.8 Measuring outcomes 3.5.6 Delivery
7.5 Resources management
7.5.1 Overview
7.5.2 Planning the project organization | 4.6.4 Hierarchy charts
7.5.3 Establishing the team | 2.4.3 Project team composition and structure 3.5.2 Project team
7.5.4 Developing the team | 4.2.6 Project team development models 2.2.3 High-performing project teams 2.2.4 Leadership skills 3.5.2 Project team
7.5.5 Managing the team | 2.2.5 Tailoring leadership styles 2.5.3 Maintaining project team focus 2.5.8 Learning throuhgout the project 2.2.1 Project team management and leadership 2.2.7 Checking results
7.5.6 Planning, managing and controlling physical and material resources | 2.4.5 Physical resources 2.4.9 Alignment 2.5.5 Managing physical resources 2.5.10 Checking results
7.6 Schedule management
7.6.1 Overview
7.6.2 Estimating activity durations | 2.4.2.3 Schedules 4.2.3 Customer and supplier perspective 4.6.5 Baselines 4.4.2 Estimating
7.6.3 Developing the schedule | 2.4.2.3 Schedules 4.6.5 Baselines 4.6.6 Visual data and information 2.4.8 Metrics
7.6.4 Controlling the schedule | 2.7.2 What to measure 2.4.8 Metrics
7.7 Cost management
7.7.1 Overview
7.7.2 Estimating cost | 2.4.2 Planning variables 4.4.2 Estimating 4.6.5 Baselines 4.6.6 Visual data and information 2.6.3.1 Cost of Quality
7.7.3 Developing the budget | 2.5.5 Managing physical resources 2.4.2.4 Budget 2.4.8 Metrics
7.7.4 Controlling costs | 2.8.4 Volatility 2.7.2.3 Baseline Performance 2.4.8 Metrics
7.8 Risk management
7.8.1 Overview
7.8.2 Identifying risk | 4.6.4 Hierarchy charts 4.6.2 Logs and registers 3.5.7 Uncertainty
7.8.3 Assessing risk | 2.8.5.1 Threats 2.8.5.2 Opportunities 4.6.2 Logs and registers 4.4.1 Data gathering and analysis
7.8.4 Treating risk | 2.8.5.1 Threats 2.8.5.2 Opportunities 2.8.5.3 Management and Contingency Reserve 2.8.5.4 Risk Review 4.6.2 Logs and registers
7.8.5 Controlling risk | 2.8.5.4 Risk Review 4.4.3 Meetings and events 4.6.7 Reports 4.6.2 Logs and registers
7.9 Issues management
7.9.1 Overview
7.9.2 Identifying issues | 4.6.2 Logs and registers 4.6.7 Reports
7.9.3 Resolving issues | 4.6.2 Logs and registers 4.6.7 Reports
7.10 Change control
7.10.1 Overview
7.10.2 Establishing a change control framework | 4.6.2 Logs and registers 4.6.3 Plans
7.10.3 Identifying and assessing change requests | 4.6.2 Logs and registers 4.6.3 Plans
7.10.4 Planning the implementation of change requests | 2.5.7 Monitoring new work and changes 4.6.2 Logs and registers 4.6.3 Plans
7.10.5 Implementing and closing change requests | 4.6.2 Logs and registers 4.6.3 Plans
7.11 Quality management
7.11.1 Overview
7.11.2 Planning quality | 2.6.3 Plans 4.6.3 Plans
7.11.3 Assuring quality | 2.6.3 Plans 2.8.1 General uncertainty 4.6.3 Plans
7.11.4 Controlling quality | 4.6.7 Reports
7.12 Stakeholder engagement
7.12.1 Overview
7.12.2 Identifying stakeholders | 2.1.1.1 Identify 2.1.1.2 Understand and Analyze 2.1.1.3 Prioritize 3.5.1 Stakeholders
7.12.3 Engaging stakeholders | 2.1.1.4 Engage 4.6.3 Plans 2.1.2 Interactions with other performance domains 2.2.6 Interactions with other performance domains 2.4.10 Interactions with other performance domains 2.5.9 Interactions with other performance domains 2.6.5 Interactions with other performance domains 2.8.6 Interactions with other performance domains 3.3.3 Engagement
7.13 Communication management
7.13.1 Overview
7.13.2 Planning communication | 2.4.4 Communication 4.2.2 Communication models 4.6.3 Plans
7.13.3 Distributing information | 2.1.1.4 Engage 4.2.2 Communication models 2.5.4 Project communications and engagement
7.13.4 Monitoring the impact of communication | 2.1.1.5 Monitor 2.5.10 Checking results
7.14 Managing organizational and societal change
7.14.1 Overview
7.14.2 Identifying the need for change | 4.2.4.1 Managing Change in Organizations
7.14.3 Implementing the organizational and societal change | 4.2.4.1 Managing Change in Organizations 4.2.4.2 ADKAR® Model 4.2.4.3 The 8-Step Process for Leading Change 4.2.4.4 Virginia Satir Change Model 4.2.4.5 Transition Model
7.15 Reporting
7.15.1 Overview
7.15.2 Planning reporting | 2.3.4.3 Organization 2.7.1 Establishing effective measures 3.5.8 Measurements 2.5.10 Checking results 2.7.3.1 Dashboards 2.8.5.4 Risk Review 4.6.7 Reports
7.15.3 Managing reporting | 2.5.10 Checking results 2.7.3.1 Dashboards 2.8.5.4 Risk Review 4.6.7 Reports
7.15.4 Delivering reports | 2.5.10 Checking results 2.7.3.1 Dashboards 2.8.5.4 Risk Review 4.6.7 Reports
7.16 Information and documentation management
7.16.1 Overview
7.16.2 Identifying which information should be managed | 2.1.1.4 Engage 2.2.4.2 Critical Thinking 2.3.6 Aligning of delivery cadence, development approach, and life cycle 2.4.4 Communication 2.4.11 Checking results 2.5.4 Project communications and engagement 2.7.1 Establishing effective measures 2.7.1.2 Effective Metrics 2.7.2.5 Business Value 2.7.6 Growing and improving 2.8.1 General uncertainty 3.5.5 Project Work
7.16.3 Storing and retrieving information and documentation | 2.2.5 Tailoring leadership styles 2.3.3 Development approaches 2.4 Planning performance domain 2.5.4 Project communications and engagement 2.5.8.2 Explicit and Tacit Knowledge 2.7.1 Establishing effective measures 2.7.3 Presenting information 2.7.3.1 Dashboards 2.7.3.2 Information Radiators 2.7.3.3 Visual Controls 2.7.7 Interactions with other performance domains 3.5.5 Project Work
7.17 Procurement
7.17.1 Overview
7.17.2 Planning procurement | 2.5 Project work performance domain 2.5.6 Working with procurements 3.5.4 Planning 4.6.3 Plans 2.4.6 Procurement
7.17.3 Evaluating and selecting suppliers
7.17.4 Administering contracts | 2.5.10 Checking results 2.3.5 Life cycle and phase definitions 2.5.6.2 Contracting 4.6.8 Agreements and contracts
7.17.5 Closing contracts
7.18 Lessons learned
7.18.1 Overview
7.18.2 Identifying lessons | 2.3.6 Aligning of delivery cadence, development approach, and life cycle 2.5.1 Project processes 2.5.8 Learning throughout the project 3.6 Diagnostics 2.7.7 Interactions with other performance domains 2.8.5.4 Risk Review 3.3.2 Processes
7.18.3 Disseminating lessons | 2.5.8 Learning throuhgout the project 3.5.5 Project Work
Overs
2.5.2 Balancing competing constraints
2.6.4 Suboptimal outcomes
2.8.2 Ambiguity
2.8.3 Complexity
2.8.7 Checking results
3.3.4 Tools
3.3.5 Methods and artifacts
4.3 Models applied across performance domains
4.4.4 Other methods
4.5 Methods applied across performance domains
4.6.9 Other artifacts
4.7 Artifacts applied across performance domains